## Summary
Week | Date | Changming Wu | Hardik Kansara | Kwinno Pineda | Patrick Cura | Weekly Total Hours
1 | 11/07/16 - 17/07/16 | 25 | 21 | 26 | 27 | 99
2 | 18/07/16 - 24/07/16 | 26 | 22 | 26 | 21 | 95
3 | 25/07/16 - 31/07/16 | 27 | 24 | 30 | 30 | 111
4 | 01/08/16 - 07/08/16 | 24 | 22 | 27.5 | 28 | 101.5
5 | 08/08/16 - 14/08/16 | 25 | 23 | 24 | 28 | 100
6 | 15/08/16 - 21/08/16 | 42.5 | 42 | 34 | 16 | 134.5
7 | 22/08/16 - 28/08/16 | 0 | 36 | 7.5 | 0 | 43.5
8 | 29/08/16 - 04/09/16 | 0 | 0 | 0 | 0 | 0
9 | 05/09/16 - 11/09/16 | 0 | 0 | 0 | 0 | 0
10 | 12/09/16 - 18/09/16 | 0 | 0 | 0 | 0 | 0
11 | 19/09/16 - 25/09/16 | 0 | 0 | 0 | 0 | 0
12 | 26/09/16 - 02/10/16 | 0 | 0 | 0 | 0 | 0
13 | 03/10/16 - 09/10/16 | 0 | 0 | 0 | 0 | 0
14 | 10/10/16 - 16/10/16 | 0 | 0 | 0 | 0 | 0
|  | 169.5 | 190 | 175 | 150 | 684.5

## Changming Wu
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Project Proposal | 12:00 pm - 04:00 pm | 4 | 25
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-07-12 | Pre-project, Feasibility and Foundation : Project Proposal | 12:00 pm - 04:00 pm | 4
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-07-13 | Pre-project, Feasibility and Foundation : Research Methodology | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-14 | Pre-project, Feasibility and Foundation : Project Proposal | 04:00 pm - 06:00 pm | 2
|  | Project Admin : Project Diary | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
2016-07-15
| 2016-07-16 | Pre-project, Feasibility and Foundation : Project Proposal | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-17 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Project Proposal | 10:30 am - 11:30 am | 1 | 26
|  | Pre-project, Feasibility and Foundation : Project Gantt Chart | 11:30 am - 03:30 pm | 4
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-19 | Pre-project, Feasibility and Foundation : Project Proposal (update project plan) | 11:00 am - 12:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal (Create personal CV) | 01:00 pm - 02:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal (update Spiral Model ) | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-20 | Pre-project, Feasibility and Foundation : Project Proposal | 11:30 am - 01:30 pm | 2
|  | Meeting : Consulting Robert For Documents Review | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 1
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-21 | Project Admin : Create Supporting Documents - team meeting agenda | 12:30 pm - 01:00 pm | 0.5
|  | Project Admin : Create Supporting Documents - project management plan | 09:00 am - 10:00 am 04:00 pm - 06:30 pm | 3.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
2016-07-22
| 2016-07-23 | Pre-project, Feasibility and Foundation : Project Proposal | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-24 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Project Admin : Create Supporting Documents -project proposal | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm -04:30 pm | 0.5
3 | 2016-07-25 | Project Admin : Create Supporting Documents -client brief document | 10:30 am - 03:30 pm | 5 | 27
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
| 2016-07-26 | Pre-project, Feasibility and Foundation - DSDM Model | 10:30 am - 02:30 pm | 4
|  | Project Admin : Project Diary | 02:30 pm - 03:00 pm | 0.5
|  | Project Admin : Personal Logs | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
| 2016-07-27 | Project Admin : Create Supporting Documents -Created team contract | 12:00 pm - 05:00 pm | 5
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
2016-07-28
2016-07-29
| 2016-07-30 | Project Admin : Create Supporting Documents - communication plan | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
| 2016-07-31 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Project Admin : Create Supporting Documents -the product assumption with DSDM | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm -04:30 pm | 0.5
4 | 2016-08-01 | Project Admin : Create Supporting Documents - advisor meeting agenda | 12:00 pm - 01:00 pm | 1 | 24
|  | Project Admin : Create Supporting Documents - project anaylsis | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-02 | Project Admin : Create Supporting Documents - project time sheet template | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - project anaylsis and system outline | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05: 30 pm | 0.5
| 2016-08-03 | Project Admin : Create Supporting Documents - Analysis and Design Documents | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05: 30 pm | 0.5
2016-08-04
2016-08-05
| 2016-08-06 | Project Admin : Create Supporting Documents - Analysis and Design Documents | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - list and confirm all documents all documents ofr project audit 1 | 01:00 pm - 03:30 pm | 1
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
5 | 2016-08-08 | Project Admin : Create Supporting Documents - data flow diagram and activity diagram | 11:00 am - 01:00 pm | 2 | 25
|  | Project Admin : Create Supporting Documents - Draft progress report for project audit 1 | 01:00 pm - 02:00 pm | 1
|  | Project Admin : Project Diary | 02:00 pm - 02:30 pm | 0.5
|  | Project Admin : Timesheet | 02:30 pm - 03:00 pm | 0.5
| 2016-08-09 | Project Admin : Create Supporting Documents - Project DSDM Project Roles Summary | 10:30 am - 04:30 pm | 5
|  | Project Admin : Project Diary | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Personal Logs | 05:00 pm - 05:30 pm | 0.5
| 2016-08-10 | Project Admin : Create Supporting Documents - Edit Gantt Chart | 11:30 am - 01:00 pm | 1.5
|  | Meeting : Weekly Meeting with Project Advisor | 03:00 pm - 04:00 pm | 1
|  | Meeting : Consulting Robert For Documents Review | 04:00 pm - 05:00 pm | 1
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
| 2016-08-11 | Project Admin : Create Supporting Documents - Meeting minutes | 12:30 pm - 01:30 pm | 1
2016-08-12
| 2016-08-13 | Project Admin : Create Supporting Documents - Review the documents for project audit 1 | 01:00 pm - 03:30 pm | 2.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-08-14 | Meeting : Frequent Face-to-Face Meeting with Team Members | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Review the documents for project audit 1 | 01:00 pm - 03:30 pm | 2.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
6 | 2016-08-15 | Project Admin : Create Supporting Documents - advisor meeting agenda | 10:30 am - 11:00 am | 0.5 | 42.5
|  | Project Admin : Create Supporting Documents - Project DSDM Terms of Reference | 11:00 am - 05:00 pm | 6
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:50 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-16 | Meeting : Weekly Meeting with Project Advisor | 11:00 am - 11:30 pm | 0.5
|  | Project Admin : Create Supporting Documents - Meeting minutes | 11:30 am - 12:30 pm | 1
|  | Project Admin : Create Supporting Documents - Edit Gantt Chart | 12:30 pm - 04:30 pm | 4
|  | Project Admin : Create Supporting Documents - Complete Progress Report for Project Audit 1 | 04:30 pm - 05:30 pm | 1
|  | Project Admin : Project Diary | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Personal Logs | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
| 2016-08-17 | Project Admin : Create Supporting Documents - prepare the documents for Project Audit 1 | 11:30 am - 02:30 pm | 3
|  | Project Audit : Project Audit 1 | 03:00 pm - 04:00 pm | 1
|  | Reflection and summary after Project Audit 1 | 04:00 pm - 06:00 pm | 2
|  | Project Admin : Personal Logs | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
|  | Project Admin : Project Diary | 07:00 pm - 07:30 pm | 0.5
| 2016-08-18 | Project Admin : Create Supporting Documents -- Requirements analysis document | 12:00 pm - 02:00 pm | 2
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Create Supporting Documents -- Team meeting agenda | 06:00 pm - 07:00 pm | 1
| 2016-08-19 | Project Admin : Create Supporting Documents -- Requirements analysis document | 01:00 pm - 04:00 pm | 3
|  | Project Admin : Project Diary | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-08-20 | Project Admin : Create Supporting Documents -- Requirements analysis document | 01:00 pm - 04:00 pm | 3
|  | Project Admin : Personal Logs | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
| 2016-08-21 | Project Admin : Create Supporting Documents - Advisor Meeting agenda | 10:30 am - 11:30 am | 1
|  | Project Admin : Create Supporting Documents - Weekly progress report (week 6) | 11:30 am - 01:30 pm | 2
|  | Project Admin : Create Supporting Documents - Edit Grantt Chart | 01:30 pm - 02:30 pm | 1
|  | Project Admin : Project Diary | 02:30 pm - 03:00 pm | 0.5
|  | Project Admin : Personal Logs | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Hardik Kansara
Week | Date | Activity (Project Tasks) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Initial Plan |  | 2 | 21
| 2016-07-11 | Pre-project, Feasibility and Foundation : Requirements Analysis |  | 2
| 2016-07-12 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-13 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-14 | Pre-project, Feasibility and Foundation : Initial Plan |  | 2
| 2016-07-15 | Project Admin : Create Supporting Documents |  | 1
2016-07-16
| 2016-07-17 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-17 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-17 | Project Admin : Personal Logs |  | 0.5
| 2016-07-17 | Project Admin : Timesheet |  | 0.5
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Research Methodology |  | 5 | 22
| 2016-07-19 | Pre-project, Feasibility and Foundation : Research Methodology |  | 5
2016-07-20
| 2016-07-21 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 5
| 2016-07-22 | Pre-project, Feasibility and Foundation : Select Methodology |  | 3
| 2016-07-23 | Pre-project, Feasibility and Foundation : Select Methodology |  | 2
| 2016-07-24 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-24 | Project Admin : Personal Logs |  | 0.5
| 2016-07-24 | Project Admin : Timesheet |  | 0.5
3 | 2016-07-25 | Pre-project, Feasibility and Foundation : Project Proposal |  | 5 | 24
| 2016-07-26 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-26 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 1
| 2016-07-27 | SQL Server R&D |  | 4
| 2016-07-27 | Meeting : Consulting Robert For Documenets Review |  | 1
| 2016-07-28 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-29 | SQL Server R&D |  | 3
2016-07-30
| 2016-07-31 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-31 | Project Admin : Personal Logs |  | 0.5
| 2016-07-31 | Project Admin : Timesheet |  | 0.5
4 | 2016-08-01 | SQL Server R&D |  | 4 | 22
| 2016-08-02 | Pre-project, Feasibility and Foundation : Project Proposal |  | 5
| 2016-08-03 | Analysis and Design Documents : Database Evaluator Analysis and Design Document |  | 2
| 2016-08-04 | Analysis and Design Documents : Website Analysis and Design Document |  | 2
| 2016-08-05 | SQL Server R&D |  | 5
| 2016-08-06 | Analysis and Design Documents : Client Application Analysis and Design Document |  | 2
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-08-07 | Project Admin : Personal Logs |  | 0.5
| 2016-08-07 | Project Admin : Timesheet |  | 0.5
5 | 2016-08-08 | Absent : Sick Leave |  |  | 23
| 2016-08-09 | Analysis and Design Documents : Client Application Analysis and Design Document |  | 4
| 2016-08-10 | Meeting : Weekly Meeting with Project Advisor |  | 0.5
| 2016-08-10 | Meeting : Consulting Robert For Documenets Review |  | 1
| 2016-08-10 | SQL Server R&D |  | 2
| 2016-08-10 | Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test |  | 2.5
2016-08-11
| 2016-08-12 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-08-13 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 4
| 2016-08-14 | SQL Server R&D |  | 5
6 | 2016-08-15 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6 | 42
| 2016-08-16 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:30 AM to 5:00 PM | 5.5
| 2016-08-16 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-08-17 | Project Audit : Project Audit 1 | 3:00 PM to 4:00 PM | 1
| 2016-08-17 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 3:00 PM | 4
| 2016-08-17 | Project Admin : Create Supporting Documents | 4:00 PM to 5:00 PM | 1
| 2016-08-18 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-19 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-20 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-21 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 3:00 PM | 4
| 2016-08-21 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-08-21 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
7 | 2016-08-22 | Project Admin : Create Supporting Documents | 11:00 AM to 2:00 PM | 3 | 36
| 2016-08-22 | Meeting : Frequent Face-to-Face Meeting with Team Members | 2:00 PM to 3:00 PM | 1
| 2016-08-22 | Project Admin : Create Supporting Documents | 3:00 PM to 5:00 PM | 2
| 2016-08-23 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-24 | Project Admin : Create Supporting Documents | 11:00 AM to 2:00 PM | 3
| 2016-08-24 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 2:00 PM to 5:00 PM | 3
| 2016-08-25 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-26 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-27 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Kwinno Pineda
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Initial Plan | 12:00pm – 5:00pm | 5 | 26
| 2016-07-12 | Pre-project, Feasibility and Foundation : Requirements Analysis | 10:30am – 4:00pm | 5.5
| 2016-07-13 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 9:00pm | 6
| 2016-07-14 | Pre-project, Feasibility and Foundation : Research Methodology | 2:00pm – 5:30pm | 3.5
| 2016-07-15 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 9:00pm | 6
2016-07-16
2016-07-17
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 4:00pm | 4 | 26
| 2016-07-19 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 7:30pm | 5
| 2016-07-20 | Meeting : Consulting Robert For Documenets Review | 2:00pm – 3:00pm | 1
| 2016-07-20 | Pre-project, Feasibility and Foundation : Select Methodology | 3:00pm – 9:00pm | 6
2016-07-21
| 2016-07-22 | Pre-project, Feasibility and Foundation : Select Methodology | 3:00pm – 9:00pm | 6
2016-07-23
| 2016-07-24 | Pre-project, Feasibility and Foundation : Select Methodology | 12:30pm – 4:30pm | 4
3 | 2016-07-25 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 09:30pm | 7 | 30
| 2016-07-26 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 9:00pm | 8
| 2016-07-27 | Pre-project, Feasibility and Foundation : Research Methodology | 1:30pm – 9:00pm | 7.5
2016-07-28
| 2016-07-29 | Pre-project, Feasibility and Foundation : Research Methodology | 5:00pm – 9:00pm | 4
2016-07-30
| 2016-07-31 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 4:30pm | 3.5
4 | 2016-08-01 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 5:00pm | 4 | 27.5
| 2016-08-02 | Pre-project, Feasibility and Foundation : Research Methodology | 12:30pm -5:00pm | 4.5
| 2016-08-03 | Analysis and Design Documents : Website Analysis and Design Document | 11:00am – 7:30pm | 8.5
2016-08-04
| 2016-08-05 | Pre-project, Feasibility and Foundation : Research Methodology | 4:00pm – 8:30pm | 4.5
2016-08-06
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members | 10am-11:30am & 1pm -4:30pm | 6
5 | 2016-08-08 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 8:00pm | 8 | 24
| 2016-08-09 | Pre-project, Feasibility and Foundation : Research Methodology | 2:00pm – 8:00pm | 6
| 2016-08-10 | Meeting with Steve then Robert | 1:00pm -5:00pm | 4
2016-08-11
| 2016-08-12 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 4:30pm | 2
2016-08-13
| 2016-08-14 | Pre-project, Feasibility and Foundation : Project Gantt Chart | 2:30pm – 4:30pm | 4
6 | 2016-08-15 | Pre-project, Feasibility and Foundation : Project Gantt Chart | 10am-11am & 2:30pm – 10:00pm | 9 | 34
| 2016-08-16 | Project Admin : Timesheet, Project Admin : Personal Logs | 10:30am – 1pm & 3:00pm – 5:00pm | 4.5
| 2016-08-17 | Project Audit: Project Audit 1 | 3:00pm – 4:00pm | 1
| 2016-08-17 | Analysis and Design Documents : Website Analysis and Design Document | 12:30pm – 3:00pm | 2.5
| 2016-08-17 | Analysis and Design Documents : Website Analysis and Design Document | 4:00pm – 7:30pm | 3.5
| 2016-08-17 | Project Admin : Timesheet | 7:30pm – 8:00pm | 0.5
| 2016-08-17 | Project Admin : Personal Logs | 7:30pm – 8:00pm | 0.5
| 2016-08-18 | Absent : Sick Leave
| 2016-08-19 | Analysis and Design Documents : Website Analysis and Design Document | 2:00pm – 4:30pm | 2.5
| 2016-08-20 | Analysis and Design Documents : Website Analysis and Design Document | 9:00pm – 11:00pm | 2
| 2016-08-21 | Project Admin : Timesheet | 4:00pm – 4:30pm | 0.5
| 2016-08-21 | Project Admin : Personal Logs | 4:00pm – 4:30pm | 0.5
| 2016-08-21 | Exploration Phase : Iteration Two : Website : Program the Register Form | 12:30pm – 4:00pm | 3.5
| 2016-08-21 | Analysis and Design Documents : Website Analysis and Design Document | 12:30pm – 4:00pm | 3.5
7 | 2016-08-22 | Exploration Phase : Iteration Two : Website : Program the Register Form | 2:30pm – 10:00pm | 7.5 | 7.5
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Patrick Cura
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Created group GIT Repository with sample code that can be used for project Helped in forming the client brief and bid (did last May) |  | 9 | 27
| 2016-07-12 | Created and Edited RACI document Updated code with setup functionalities and database connection capabilites |  | 7
| 2016-07-13 | Updated RACI Researched and created sample code for writing to xml, reading xml and creating a pdf Updated code for creating installer |  | 7
2016-07-14
2016-07-15
2016-07-16
| 2016-07-17 | Created Group Sked File Added Technologies Used File Team meeting |  | 4
2 | 2016-07-18 | Updated Project Proposal Analysis Section |  | 4 | 21
| 2016-07-19 | Created CV for Project Proposal Created Plans and Procedures with Hardik Updated Spiral Model Document Applied some sample queries to sample code |  | 5
| 2016-07-20 | Had Project Proposal meeting with Robert Uploaded meeting recording and scans Updated sample GUI for project Updated Project Analysis based on Robert's comments |  | 6
2016-07-21
2016-07-22
| 2016-07-23 | Added project resources file |  | 1
| 2016-07-24 | Edited Executive Summary Edited Opportunity Context Team meeting |  | 5
3 | 2016-07-25 | Added some functionalities to sample code: - Ability to get server names from machine - Fixed Visual Studio Debug not working - Updated DB Connection Code |  | 7 | 30
| 2016-07-26 | Updated System Outline Updated DB connection code again Added instances dropdown to sample UI |  | 7
| 2016-07-27 | Added Splash Screen to sample UI Edited Server Dropdown UI Edited server connection string as errors are being encountered in some instances Updated git ignore settings |  | 6
2016-07-28
2016-07-29
| 2016-07-30 | Added progress bar to sample UI Relinked Splash resources which was causing errors Added sample code for creating xml from tables |  | 5
| 2016-07-31 | Updated sample code for XML retrieval Uploaded meeting notes Added initial time box items Updated DSDM methodology document Added Diagram for project Team meeting |  | 5
4 | 2016-08-01 | Updated sample code to use threads for background processing Updated DSDM methodology Updated Project Diagram Added sample GUI with Progress Table |  | 7 | 28
| 2016-08-02 | Updated Project Analysis Updated Project Proposal Updated sample code for GUI progress table |  | 10
| 2016-08-03 | Updated time box items Updated logos for splash screen and main app Updated sample code which allows disabling of resizing of windows form |  | 6
2016-08-04
2016-08-05
2016-08-06
| 2016-08-07 | Updated time sheet and had project meeting Added sample code for encrypting files and saving files Team meeting |  | 5
5 | 2016-08-08 | Improved sample code for saving file in any directory Created Use Case diagram Drafted Activity diagram |  | 5 | 28
| 2016-08-09 | Added sample code for getting list of databases |  | 4
| 2016-08-10 | Had Adviser meeting and meeting with Robert Updated group timesheet |  | 4
2016-08-11
2016-08-12
| 2016-08-13 | Tried making the code work in other machines. Encountered some compatibility issues and had to research how to go around it. |  | 7
| 2016-08-14 | Helped edit the proposal. Formatted UI of sample code. Team meeting |  | 8
6 | 2016-08-15 | Updated the sample UI. Added new possible features to it like testing a connection first and fixing the logic in the UI. Added Icon. Added Tests for Client Application. |  | 8 | 16
| 2016-08-16 | Created Client Application Diagrams Updated Tests Updated Windows Forms Components Created Database Evaluator sample code and UI |  | 8
2016-08-17
2016-08-18
2016-08-19
2016-08-20
2016-08-21
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Project Tasks
Task Name | Comments
Pre-project, Feasibility and Foundation : Initial Plan
Pre-project, Feasibility and Foundation : Project Proposal
Pre-project, Feasibility and Foundation : Scope of Project
Pre-project, Feasibility and Foundation : Requirements Analysis
Pre-project, Feasibility and Foundation : Research Methodology
Pre-project, Feasibility and Foundation : Select Methodology
Pre-project, Feasibility and Foundation : Project Gantt Chart
Pre-project, Feasibility and Foundation : Meet Project Advisor
Pre-project, Feasibility and Foundation : Meet Co-ordinator
Pre-project, Feasibility and Foundation : Co-ordinator Approval
Pre-project, Feasibility and Foundation : Complete Project Proposal
Pre-project, Feasibility and Foundation : Complete Gantt Chart
Analysis and Design Documents : Website Analysis and Design Document
Analysis and Design Documents : Client Application Analysis and Design Document
Analysis and Design Documents : Database Evaluator Analysis and Design Document
Exploration Phase : Iteration One : Website : Plan Website and Choose Wordpress Template
Exploration Phase : Iteration One : Submit Test Report Iteration One (Website)
Exploration Phase : Iteration One : exe App: Client Application Design
Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App)
Exploration Phase : Iteration Two : Website : Program the Register Form
Exploration Phase : Iteration Two : Website : Program the Login Form
Exploration Phase : Iteration Two : Website : Verification of the Customer Email Address
Exploration Phase : Iteration Two : Website : Basic Account User Page
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (Website)
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (.exe App)
Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website
Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (Website)
Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server
Exploration Phase : Iteration Three : exe App : Completely Working GUI
Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing
Exploration Phase : Iteration Three : exe App : Encrypted Dumpfile with Testing
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App)
Engineering : Iteration One : Website: Upload of Customer Parameters or PDF to Website
Engineering : Iteration One : Website: Forgot Password Function Page
Engineering : Iteration One : Submit Test Report Iteration One (Website)
Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing
Engineering : Iteration One : Submit Test Report Iteration One (.exe App)
Engineering : Iteration Two : Website: Create Documentation Page
Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
Engineering : Iteration Two : Website: Add Plugins and Review all links
Engineering : Iteration Two : Submit Test Report Iteration Two (Website)
Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing
Engineering : Iteration Two : Submit Test Report Iteration Two (.exe App)
Engineering : Iteration Three : Website : Notification Email for Customer and Developer
Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
Engineering : Iteration Three : Submit Test Report Iteration Three (Website)
Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
Engineering : Iteration Three : Submit Test Report Iteration Three (.exe App)
Deployment : Combine Website, Client Application and Database Evaluator
System Test : Test Plan for System Test
System Test : Test Case for System Test
System Test : Test Results for System Test
System Test : Check all the Phases If all Requirements were Delivered
Post Project : Review Project
Post Project : Collating Documents
Project Admin : Project Diary
Project Admin : Personal Logs
Project Admin : Timesheet
Project Admin : Create Supporting Documents
Meeting : Frequent Face-to-Face Meeting with Team Members
Meeting : Weekly Meeting with Project Advisor
Meeting : Consulting Robert For Documents Review
Project Audit : Project Audit 1
Project Audit : Project Audit 2
Presentation Preparation : Project Presentation
C# R&D
SQL Server R&D | Building SQL Server Scripts and Test
WordPress R&D
Absent : Sick Leave