## DBE
Start Date | End Date | Task Name | Total Hours
2016-07-11 | 2016-07-17 | Project Proposal
2016-07-18 | 2016-07-24 | Project proposal suggested changes
Identifying new methodoly for project
Aling team and all other documents as per new methodology
2016-07-25 | 2016-07-31
2016-08-01 | 2016-07-07

## DayToDay
Start Date | Task Name | Description | Time
2016-07-11 | Working on Project Proposal | Identifying exact requirement and team discussion about project | 4
2016-07-12 | Working on Project Proposal | Start drafting initial document for project proposal. | 5
2016-07-13 | SQL R&D | Setup VMs (Windows 2008 R2 and windows 2012) for further R&D | 3
2016-07-17 |  | Team gather for finilize project proposal. | 3
|  | Update weekly Log | 1
|  | Team meeting | 1
2016-07-18 |  | Study different methodology for project | 5
2016-07-18 |  | Analysis on different methodology and discussion with team | 2
2016-07-20 | SQL R&D | SQL Server installation for testing | 4
2016-07-21 | SQL R&D | SQL Server installation for testing | 5
2016-07-24 |  | Team gather for dicussion on new methodology for project | 4
2016-07-24 |  | Team meeting | 1
|  | Update weekly Log | 1
2016-07-25 |  | Updated Executive Summary and Opportunity Context | 5
2016-07-26 |  | Updated System Outline, SQL Server 2012 installation | 5
2016-07-27 |  | SQL Server instance configuration with Patrick and Identify the options and queries to get all SQL instances in network | 4
|  | Meeting with learning commance | 1
2016-07-30 |  | Create windows 2012 with SQL 2012 VM for testing connection string and all | 3
2016-07-31 |  | Finalize the project proposal. | 4
|  | Team meeting | 1
|  | Update weekly Log | 1
2016-08-01 |  | Testing XML object retrieve in SQL Server 2012 | 4
2016-08-01 |  | Change Project Analysis | 5
2016-08-02 |  | Change Project Proposal | 5
2016-08-03 |  | Website layout discussion with Kwino | 2
2016-08-05 |  | Lay out and analysis document design discussion with team | 1
2016-08-05 |  | SQL Server R&D | 4
2016-08-07 |  | Team meeting | 1
|  | Update weekly Log | 1
2016-08-08 |  | Absent for the day
2016-08-09 |  | UML/Activity Diagram | 4
2016-08-10
2016-08-11 |  | Meeting with Robert and Steve | 2
|  | Testing scripts and design with Patrick | 4
2016-08-12 |  | Update project proposal - changes suggested by Robert | 4
2016-08-13 |  | SQL Server 2008 installation | 4
2016-08-14 |  | Update project proposal, Client Brief and Team conctract - suggestion by Steve | 4
|  | Update weekly Log, Team meeting | 1
2016-08-15 |  | Drafting Requirement Analysis document | 6
2016-08-16 |  | Updating Analysis document & Steve meeting | 6
2016-08-17 |  | Project Audit 1, Create supporting document for audit | 6
2016-08-18 |  | Create new folder structure and update needed documents | 6
2016-08-19 |  | Time sheet create and align and weekly report formatting | 6
2016-08-20 |  | Updating Requirement Analysis document | 6
2016-08-21 |  | Update weekly Log, time card and finalize analysis document | 6
2016-08-22 |  | Requirement Analsysis Document Final update | 6
2016-08-23 |  | Create other document (Foundation Phase), Create folder structure for DSDM Templated, Assing and guide team to create technical docuements for foudantion phase | 6
2016-08-24 |  | Drafting analysis and design documents and drafting milestone document | 6
2016-08-25
2016-08-26
2016-08-29 |  | SQL Server client script for SQL Server Version and Service Pack and testing | 6
2016-08-30 |  | Meeting with Steve, create and test script for Max Degree Of Parallelism | 5
2016-08-31 |  | Update system analysis and design document ater Steve commnets | 6
2016-09-01 |  | Update system analysis and design document ater Steve commnets | 4.5
2016-09-02 |  | Update system analysis and design document ater Steve commnets | 4.5
2016-09-03 |  | Combine all the scripts and test for Patrick | 6
2016-09-04 |  | Update weekly Log, time card and finalize analysis document | 6
2016-09-05 |  | Install SQL Server 2012 on windows 2008 R2 | 6
2016-09-06 |  | Meeting with Steve, Install SQL Server 2012 on windows 2012 | 6
2016-09-07 |  | Client script : SQL Server authentication & Network Port, Team meeting | 6
2016-09-08 |  | Client script : Datafile implementation, recovery mode & compability level | 6
2016-09-09 |  | Client script : Auto create statistics, shrink, Daily index rebuild, full backup | 6
2016-09-10 |  | Audit 2, Testing final client script | 6
2016-09-11 |  | Update weekly Log, time card and testing client app | 6
2016-09-12 |  | Final Test Report for Client Application, Sing off documents for exploration Phase | 6
2016-09-13 |  | Meeting with Steve, Team Meeting, Database Evaluation Basic GUI | 6
2016-09-14 |  | Database Evaluation Script : Create Database with Basic Table and Information | 6
2016-09-15 |  | Update system analysis and design document, Database Evaluation Script : SQL Server Instance : Installation | 6
2016-09-16 |  | Database Evaluation Script : SQL Server Instance : Configuration | 6
2016-09-17 |  | Database Evaluation Script : SQL Server Instance : Security | 6
2016-09-18 |  | Update weekly Log & Time Card | 2
2016-09-19 |  | Database Evaluation Script : SQL Server Instance : Implemetation | 6
2016-09-20 |  | Database Evaluation Script : SQL Server Instance : Configuration Options | 6
2016-09-21 |  | Database Evaluation Script : SQL Server Instance : Configuration Options | 6
2016-09-22 |  | Database Evaluation Script : SQL Server Instance : Configuration Options | 5
2016-09-23 |  | Database Evaluation Script : SQL Server Instance : Maintenance | 5
2016-09-24 |  | Update system analysis and design document, Database Evaluation Script : SQL Server Instance : Maintenance | 5
2016-09-25 |  | Update weekly Log & Time Card | 2
2016-09-25 |  | Database Evaluation Script : SQL Server Instance : Maintenance | 6
2016-09-26 |  | Database Evaluation Script : SQL Server Instance : Maintenance | 6
2016-09-27 |  | Database Evaluation Script : SQL Server Instance : Security | 6
2016-09-28 |  | Testing Script | 4
2016-09-29 |  | Testing Script | 4
2016-09-30 |  | Testing Script | 4
2016-10-01
2016-10-02 |  | Update weekly Log & Time Card | 2