## Website
Bug List for Website
ID | Severity | Priority | Status | Result | Comment
W001 | B | B |  | Register Page: After registered, user can not receive the confirmation email
W002 | E | E |  | Login Page: The content of pop-up message is wrong ERROR: Invalid email address. Lost your password? | Invalid email address --> Invalid username/email
W003 | B | B |  | Forgot Password Page: Cannot get new password. | The email could not be sent. Possible reason: your host may have disabled the mail() function.
W004 | D | E |  | Home Page: Change the fill colour of Subscribe button
W005 | E | E |  | Documentation Page: change the title of help document
W006 | E | E |  | Documentation Page: add the page number of the help document
W007 | D | D |  | Contact Page: Input the incorrect email still can send the contact message
W008 | B | D |  | About Page: Click Next Page can not open the next page | 404 (Page Not Found) Error
W009 | D | E |  | Upload Page: Change the fill colour of Select File Button
W010 | D | E |  | Upload Page: Change the fill colour of Upload File Button
W011 | B | B |  | Upload Page: Cannot upload the dbe file
W012 | B | B |  | Dashboard: Cannot send the report to user | The attached file is missing/deleted.

## Client Application
Bug List for Client Application
ID | Severity | Priority | Status | Result | Comment
CA001 | D | E |  | Can not select the save path
CA002 | C | C |  | The value of server name list is wrong. | The current testing machine is not installed any server, the server name list still has value.
CA003 | D | D |  | The Client Application does not in the front of current window when it has been executed.
CA004 | D | D |  | After generated the dump file, the database name becomes can be selected. | The current testing machine does not install any database or it does not install and database on the selected server
CA005 | D | D |  | The generated dump file is empty when using normal user to execute the Client Application | Suggest: to add the text label on the application to inform run this application as administrator
CA006 | D | E |  | After generated the dump file, does not have the pop-up message | Suggest: to increase the pop-up message when finished generating file

## Database Evaluator
Bug List for Database Evaluator
ID | Severity | Priority | Status | Result | Comment
DB001 | D | D |  | Just gives the default same name of report | Suggest: to give the same name as seleted dbe file
DB002 | D | E |  | After generated the report, does not have the pop-up message | Suggest: to increase the pop-up message when finished generating the report
DB003 | D | D |  | Lack the headline of Consolidated Scorecard table | Severity, Type, Parameter, Status
DB004 | D | D |  | Lack page number of report | Add the page number of report
DB005 | D | D |  | Does not display the status on the details of each parameter | Suggest: to increase the status of each checked parameter to show it passed or no passed
DB006 | D | C |  | Can not open the reference link when using the browse to open the PDF | See the sheet of "Reference Link Test"
DB007 | C | C |  | The content of Trace flag 1117 and Trace flag 1118 are wrong. | Trace flag 1117 has shown the content of Trace flag 1118 and Trace flag 1118 has shwon the content of Trace flag 1117.
DB008 | D | C |  | The parameter has past but it still shown the issue of the passed item. | If there is no issues in this item , just show the passed status.
DB009 | C | C |  | The value of Auto Shriuk is wrong | The value always displays the past status even the setting of this item is faluse
DB010 | C | C |  | The value of Compatibility level is wrong | The compatibility level is setting 90 (SQL Sever 2005 (90))
DB011 | C | C |  | The value of Max Degree of Parallelism is wrong | The value always displays the no past status even the setting of this item is 32
DB012 | C | C |  | The value of Server authentication is wrong | The value is setting Windows Authertication mode, the status of this item is still displays no-pass.
DB013 | C | C |  | The value of Memory- Min Memory is wrong | Memory- Min Memory is wrong is setting 2000000000, the status still displays passed.
DB014 | C | C |  | The detail content of Memory- Min Memory is wrong | The details content of Memory- Min Memory and Memory- Max Memory are the same.

## Reference Link Test
Bug List for Reference Link
ID | Severity | Priority | Status | Parameter | Reference 1 | Reference 2
RL001 | D | D |  | Daily database Full backup | The page you requested cannot be found. | 404 - File or directory not found.
RL002 | D | D |  | NT AUTHORITY\SYSTEM Administrator | The page you requested cannot be found.
RL003 | D | D |  | Read Committed Snapshot | The page you requested cannot be found.
RL004 | D | D |  | Snapshot Isolation | The page you requested cannot be found.
RL005 | D | D |  | SQL Server Instance Installation Directory | Try searching for what you need
RL006 | D | D |  | SQL Server Network Port | The page you requested cannot be found.
RL007 | D | D |  | SQL Server Version and Service Pack | Try searching for what you need | Try searching for what you need
RL008 | D | D |  | Default index fill factor | The page you requested cannot be found.
RL009 | D | D |  | Trace flag 1117 | The page you requested cannot be found.
RL010 | D | D |  | Trace flag 1118 | The page you requested cannot be found.
RL011 | D | D |  | Trace flag 2371 | The page you requested cannot be found.
RL012 | D | D |  | Max Degree Of Parallelism | The page you requested cannot be found.
RL013 | D | D |  | Server authentication | The page you requested cannot be found. | 404 - File or directory not found.
RL014 | D | D |  | Recovery Model | The page you requested cannot be found.
RL015 | D | D |  | Blank SQL SA Password | The page you requested cannot be found. | 404 - File or directory not found.
RL016 | D | D |  | Memory - Max Memory | The page you requested cannot be found.
RL017 | D | D |  | Memory - Min Memory | The page you requested cannot be found.

## Sverity & Priority
Severity
ID | Level | Definition
A | Blocker | The system can not be executed, crashes or a serious shortage of resources, the application module can not start or abnormal exit, unable to test, resulting in system instability.
B | Critical | The impact of system functions or operations, the main function there are serious flaws, but will not affect the system stability.
C | Major: | The user does not implement the basic functions of the implementation, there is a reasonable way to correct, the user can perform basic operations.
D | Minor | The operator is not convenient to use, but does not affect the function of the realization. Can improve the function.
E | Cosmetic | The ease of use and the proposed features
Priority
ID | Level | Definition
A | Immediate | "Immediately resolve" that the problem must be resolved immediately, otherwise the system simply can not meet the scheduled needs.
B | Urgent | Urgent need to solve, said the repair of the problem is very important, very urgent, related to the system's main function module can be normal.
C | High | "A high degree of attention", that there is time to be resolved immediately, or the system deviation from the larger demand or scheduled functions can not be normal.
D | Normal | Normal processing into the personal plan to solve, said the problem does not affect the realization of demand, but affect other aspects of use.
E | Low | Low priority, that is, the problem must be confirmed before the release of the system can be resolved or confirmed to be resolved.

## Bug Status
Bug status
Status | Definition
New | When a new defect is logged and posted for the first time. It is assigned a status NEW.
Assigned | Once the bug is posted by the tester, the lead of the tester approves the bug and assigns the bug to developer team.
Open | The developer starts analyzing and works on the defect fix
Fixed | When developer makes necessary code change and verifies the change, he or she can make bug status as "Fixed."
Pending retest | Once the defect is fixed the developer gives particular code for retesting the code to the tester. Since the testing remains pending from the testers end, the status assigned is "pending request."
Retest | Tester does the retesting of the code at this stage to check whether the defect is fixed by the developer or not and change the status to "Re-test."
Verified | The tester re-tests the bug after it got fixed by the developer. If there is no bugdetected in the software, then the bug is fixed and the status assigned is "verified."
Reopen | If the bug persists even after the developer has fixed the bug, the tester changes the status to "reopened". Once again the bug goes through the life cycle.
Closed | If the bug is no longer exits then tester assign the status "Closed."
Duplicate | If the defect is repeated twice or the defect corresponds the same concept of the bug, the status is changed to "duplicate."
Rejected | If the developer feels the defect is not a genuine defect than it changes the defect to "rejected."
Deferred | If the present bug is not of a prime priority and if it is expected to get fixed in the next release, then status "Deferred" is assigned to such bugs.
Not a bug | If it does not affect the functionality of the application then the status assigned to a bug is "Not a bug".