## Summary
Week | Date | Changming Wu | Hardik Kansara | Kwinno Pinede | Patrick Cura | Weekly Total Hours
1 | 11/07/16 - 17/07/16 | 0 | 21 | 26 | 24 | 71
2 | 18/07/16 - 24/07/16 | 0 | 22 | 21 | 21 | 64
3 | 25/07/16 - 31/07/16 | 0 | 0 | 30 | 30 | 60
4 | 01/08/16 - 07/08/16 | 0 | 0 | 26.5 | 28 | 54.5
5 | 08/08/16 - 14/08/16 | 0 | 0 | 24.5 | 25 | 49.5
6 | 15/08/16 - 21/08/16 | 0 | 0 | 9 | 0 | 9
7 | 22/08/16 - 28/08/16 | 0 | 0 | 0 | 0 | 0
8 | 29/08/16 - 04/09/16 | 0 | 0 | 0 | 0 | 0
9 | 05/09/16 - 11/09/16 | 0 | 0 | 0 | 0 | 0
10 | 12/09/16 - 18/09/16 | 0 | 0 | 0 | 0 | 0
11 | 19/09/16 - 25/09/16 | 0 | 0 | 0 | 0 | 0
12 | 26/09/16 - 02/10/16 | 0 | 0 | 0 | 0 | 0
13 | 03/10/16 - 09/10/16 | 0 | 0 | 0 | 0 | 0
14 | 10/10/16 - 16/10/16 | 0 | 0 | 0 | 0 | 0
|  | 0 | 43 | 137 | 128 | 308

## Changming Wu
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 |  |  |  | 0
2016-07-12
2016-07-13
2016-07-14
2016-07-15
2016-07-16
2016-07-17
2 | 2016-07-18 |  |  |  | 0
2016-07-19
2016-07-20
2016-07-21
2016-07-22
2016-07-23
2016-07-24
3 | 2016-07-25 |  |  |  | 0
2016-07-26
2016-07-27
2016-07-28
2016-07-29
2016-07-30
2016-07-31
4 | 2016-08-01 |  |  |  | 0
2016-08-02
2016-08-03
2016-08-04
2016-08-05
2016-08-06
2016-08-07
5 | 2016-08-08 |  |  |  | 0
2016-08-09
2016-08-10
2016-08-11
2016-08-12
2016-08-13
2016-08-14
6 | 2016-08-15 |  |  |  | 0
2016-08-16
2016-08-17
2016-08-18
2016-08-19
2016-08-20
2016-08-21
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Hardik Kansara
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Identifying exact requirement and team discussion about project |  | 4 | 21
| 2016-07-12 | Start drafting initial document for project proposal. |  | 5
| 2016-07-13 | Setup VMs (Windows 2008 R2 and windows 2012) for further R&D |  | 3
| 2016-07-14 | Update project proposal document |  | 4
2016-07-15
2016-07-16
| 2016-07-17 | Team meeting, Update weekly Log and finilize project proposal. |  | 5
2 | 2016-07-18 | Study different methodology for project, Analysis on different methodology and discussion with team |  | 7 | 22
2016-07-19
| 2016-07-20 | SQL Server installation for testing |  | 4
| 2016-07-21 | SQL Server installation for testing |  | 5
2016-07-22
2016-07-23
| 2016-07-24 | Team meeting, Update weekly Log and finilize new methodology |  | 6
3 | 2016-07-25 |  |  |  | 0
2016-07-26
2016-07-27
2016-07-28
2016-07-29
2016-07-30
2016-07-31
4 | 2016-08-01 |  |  |  | 0
2016-08-02
2016-08-03
2016-08-04
2016-08-05
2016-08-06
2016-08-07
5 | 2016-08-08 |  |  |  | 0
2016-08-09
2016-08-10
2016-08-11
2016-08-12
2016-08-13
2016-08-14
6 | 2016-08-15 |  |  |  | 0
2016-08-16
2016-08-17
2016-08-18
2016-08-19
2016-08-20
2016-08-21
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Kwinno Pinede
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Talk about the Project Proposal and Methodology(Spiral), Assigning of Roles |  | 5 | 26
| 2016-07-12 | Took some notes and listen to Robert Class, Read the Guidelines and Planning to take SAD book from the Library |  | 5.5
| 2016-07-13 | Reviewing methodology to use, read the EBHost article and search Internet, took SAD book read the first 5 pages and take it home with me |  | 6
| 2016-07-14 | Ask Patrick about the Methodology, Scanned the SAD book, Read online article for methodology |  | 3.5
| 2016-07-15 | Review methodology look at the S:, print out the MSF, DSDM and XP methodology |  | 6
2016-07-16
2016-07-17
2 | 2016-07-18 |  |  |  | 21
| 2016-07-19 | Attend Robert class, Create the Approach section for Spiral |  | 5
| 2016-07-20 | Robert check our proposal, read the DSDM methodology and OpenUp |  | 6
2016-07-21
| 2016-07-22 | Read Agile Metodology vs. Traditional, Reading Agile whats best to use, what are the available options, how to apply it and many more. |  | 6
2016-07-23
| 2016-07-24 | Discuss the DSDM to member, Read DSDM again, help PM for any task he needs help |  | 4
3 | 2016-07-25 | Read the DSDM Atern in the Project in a Box,still reading articles, Reviewing the template to use to project |  | 7 | 30
| 2016-07-26 | Studying DSDM Lifecycle, Core techniques, Roles, Deadlines |  | 8
| 2016-07-27 | Watch Video tutorial of DSDM on youtube, read some articles DSDM |  | 7.5
2016-07-28
| 2016-07-29 | Read the Atern Handbook on the dsdm.org and study it much detailed over 50 pages I think |  | 4
2016-07-30
| 2016-07-31 | Set dates to the DSDM atern Life cycle |  | 3.5
4 | 2016-08-01 | Did the Approach and Project Analysis for methodology to the proposal, book Learning commons to proof read |  | 4 | 26.5
| 2016-08-02 | Check the Proposal and Approach and Project Analysis, Ask Learning common to check proposal |  | 4.5
| 2016-08-03 | Attend Mariki workshop, fix errors advice from Learning commons, Did the Planning of website some design and created the logo. |  | 8.5
2016-08-04
| 2016-08-05 | Write some of the diary and thinking analysis for almost 4 hours about the deadlines and methodology |  | 4.5
2016-08-06
| 2016-08-07 | Timebox assigned each member for the coming week, ask member what their task for the whole project |  | 5
5 | 2016-08-08 | Read the Project Guidelines whole, continue reading the Atern Handbook from their website |  | 8 | 24.5
| 2016-08-09 | Found a synopsis about the DSDM sample project management read it and tryin to planned again the project what to do prioritizing, template Project in a Box |  | 6
| 2016-08-10 | Meeting with Steve then Robert |  | 4
2016-08-11
| 2016-08-12 | Write down the Core techniques function and what is the importance of it |  | 2.5
2016-08-13
| 2016-08-14 | Edit and fix Project analysis and Approach, listed the weeks left, study the Gantt chart |  | 4
6 | 2016-08-15 | Fix the Gantt chart, Check Diary and Timesheet |  | 9 | 9
2016-08-16
2016-08-17
2016-08-18
2016-08-19
2016-08-20
2016-08-21
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Patrick Cura
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Created group GIT Repository with sample code that can be used for project |  | 6 | 24
| 2016-07-12 | Created and Edited RACI document Updated code with setup functionalities and database connection capabilites |  | 7
| 2016-07-13 | Updated RACI Researched and created sample code for writing to xml, reading xml and creating a pdf Updated code for creating installer |  | 7
2016-07-14
2016-07-15
2016-07-16
| 2016-07-17 | Created Group Sked File Added Technologies Used File |  | 4
2 | 2016-07-18 | Updated Project Proposal Analysis Section |  | 4 | 21
| 2016-07-19 | Created CV for Project Proposal Created Plans and Procedures with Hardik Updated Spiral Model Document Applied some sample queries to sample code |  | 5
| 2016-07-20 | Had Project Proposal meeting with Robert Uploaded meeting recording and scans Updated sample GUI for project Updated Project Analysis based on Robert's comments |  | 6
2016-07-21
2016-07-22
| 2016-07-23 | Added project resources file |  | 1
| 2016-07-24 | Edited Executive Summary Edited Opportunity Context |  | 5
3 | 2016-07-25 | Added some functionalities to sample code: - Ability to get server names from machine - Fixed Visual Studio Debug not working - Updated DB Connection Code |  | 7 | 30
| 2016-07-26 | Updated System Outline Updated DB connection code again Added instances dropdown to sample UI |  | 7
| 2016-07-27 | Added Splash Screen to sample UI Edited Server Dropdown UI Edited server connection string as errors are being encountered in some instances Updated git ignore settings |  | 6
2016-07-28
2016-07-29
| 2016-07-30 | Added progress bar to sample UI Relinked Splash resources which was causing errors Added sample code for creating xml from tables |  | 5
| 2016-07-31 | Updated sample code for XML retrieval Uploaded meeting notes Added initial time box items Updated DSDM methodology document Added Diagram for project |  | 5
4 | 2016-08-01 | Updated sample code to use threads for background processing Updated DSDM methodology Updated Project Diagram Added sample GUI with Progress Table |  | 7 | 28
| 2016-08-02 | Updated Project Analysis Updated Project Proposal Updated sample code for GUI progress table |  | 10
| 2016-08-03 | Updated time box items Updated logos for splash screen and main app Updated sample code which allows disabling of resizing of windows form |  | 6
2016-08-04
2016-08-05
2016-08-06
| 2016-08-07 | Updated time sheet and had project meeting Added sample code for encrypting files and saving files |  | 5
5 | 2016-08-08 | Improved sample code for saving file in any directory Created Use Case diagram Drafted Activity diagram |  | 5 | 25
| 2016-08-09 | Added sample code for getting list of databases |  | 4
| 2016-08-10 | Had Adviser meeting and meeting with Robert Updated group timesheet |  | 4
2016-08-11
2016-08-12
| 2016-08-13 | Tried making the code work in other machines. Encountered some compatibility issues and had to research how to go around it. |  | 7
| 2016-08-14 | Helped edit the proposal. Formatted UI of sample code. |  | 5
6 | 2016-08-15 |  |  |  | 0
2016-08-16
2016-08-17
2016-08-18
2016-08-19
2016-08-20
2016-08-21
7 | 2016-08-22 |  |  |  | 0
2016-08-23
2016-08-24
2016-08-25
2016-08-26
2016-08-27
2016-08-28
8 | 2016-08-29 |  |  |  | 0
2016-08-30
2016-08-31
2016-09-01
2016-09-02
2016-09-03
2016-09-04
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16