## Project Diary
Week | Date | Project Dialy tasks and outcomes | Issues
1 | Monday, July 11, 2016 | 1.Discussed and identified the contents of project 2.Planned and listed all documents
| Tuesday, July 12, 2016 | 1.Drafted the initial project proposal 2.Created and Edited RACI document
| Wednesday, July 13, 2016 | 1.Did research of Methodology -- Spiral Model 2.Created team meeting agenda
| Thursday, July 14, 2016 | 1.Combined and edited the project proposal
Friday, July 15, 2016
Saturday, July 16, 2016
| Sunday, July 17, 2016 | 1.Held team meeting 2.Edited project proposal 3.Created team meeting minutes | 1.We have not confirm the project advisor. 2.Security data issue
2 | Monday, July 18, 2016 | 1.Discussed and seleted methodology 2.Edited project proposal -- approach 3.Updated Project Proposal Analysis Section 4.Drafted project plan/gantt chart
| Tuesday, July 19, 2016 | 1.Discussed project plan with team members 2.Updated project plan--the Approach section for Spiral 3.Created personal CV for project proposal 4.Updated Spiral Model Document
| Wednesday, July 20, 2016 | 1.Had meeting with Robert to discuss the project proposal 2.Edited the project proposal with Robert's suggestion | Project Proposal issues: the content of executive summary: should include what,why, who, when and use the layout of common business documents project personnel: project requirements: Project analysis: system outlin Research References: Create XML from DB Query: http://stackoverflow.com/questions/18654157/how-to-make-sql-query-result-to-xml-file Writing to XML in C#: http://csharp.net-informations.com/xml/xml-from-sql.htm Generating PDF reports using C#: http://www.codeproject.com/Articles/686994/Create-Read-Advance-PDF-Report-using-iTextSharp-in
| Thursday, July 21, 2016 | 1.Created team meeting agenda 2.Created project management plan
| Friday, July 22, 2016 | 1.Did research of Methodology -- DSDM Model | DSDM Atern research: https://www.dsdm.org/content/foreword-0 the content of DSDM Atern methodology, 5 phases in the lifecycle of DSDM: Pre-Project Phase, Feasibility and Foundation Phase, Exploration Phase, Engineering Phase, Deployment Phase
| Saturday, July 23, 2016 | C# R&D SQL Server R&D | Research References: Generating PDF reports using C#: http://www.c-sharpcorner.com/blogs/create-table-in-pdf-using-c-sharp-and-itextsharp Get all SQL Server database instances: https://msdn.microsoft.com/en-us/library/a6t1z9x2%28v=vs.110%29.aspx Get all SQL Server database instances: http://stackoverflow.com/questions/10781334/how-to-get-list-of-available-sql-servers-using-c-sharp-code Get all SQL Server database instances: https://msdn.microsoft.com/en-us/library/a6t1z9x2%28v=vs.110%29.aspx Connecting to the SQL Server Database in C#: http://stackoverflow.com/questions/12862604/c-sharp-connect-to-database-and-list-the-databases Splash Form implementation: http://www.telerik.com/support/kb/winforms/forms-and-dialogs/details/add-splashscreen-to-your-application Contents of a System Architecture Definition: https://www.dsdm.org/content/products-0
| Sunday, July 24, 2016 | 1.Held team meeting 2.Edited project proposal(Executive Summary & Opportunity Context) 3.Created team meeting minutes
3 | Monday, July 25, 2016 | 1.Created client brief document
| Tuesday, July 26, 2016 | 1.Did research and studied of Methodology -- DSDM Model 2.Edited project proposal (System Outline) -- with Robert's suggestion
| Wednesday, July 27, 2016 | 1.Discussed and Created team contract
| Thursday, July 28, 2016 | 1.Created communication plan
Friday, July 29, 2016
Saturday, July 30, 2016
| Sunday, July 31, 2016 | 1.Held team meeting 2.Discussed and confirmed the product assumption with DSDM 3.Created team meeting minutes 4.Updated DSDM methodology document | The supportive documents of DSDM which are recommened of the Project in the box. We should pick up and tailor the suitable and needful documents for our project. After the discussion, we picked up the documents and allocated the responsibility of these as the following list: 1.Pre-Project Phase 2.Feasibility and Foundation Phase 3.Exploration Phase 4.Engineering Phase 5.Deployment Phase
4 | Monday, August 01, 2016 | 1.Created advisor meeting agenda 2.Edited project proposal -- project anaylsis and system outline 3.Updated Project Diagram
| Tuesday, August 02, 2016 | 1.Created and conbined project time sheet template 2.Edited project proposal -- project anaylsis and system outline
| Wednesday, August 03, 2016 | 1.Edited project proposal -- deliverables 2.Discussed the layout of website
Thursday, August 04, 2016
Friday, August 05, 2016
Saturday, August 06, 2016
| Sunday, August 07, 2016 | 1.Held team meeting 2.listed and confirmed all documents for project audit 1 3.Created team meeting minutes | Behind the planning schedule, each team did not spend enough for each week (in the original plan, every team should spend 31 hours for each week) In order to catch up the behind schedule, project team will use fast tracking to do some tasks as the same time. as the estimation of project team, we will spend 3 weeks and we will totally catch up the behind schedule as the end of week 8.
5 | Monday, August 08, 2016 | 1.Discussed data flow diagram 2.Discussed activity diagram 3.Drafted progress report for project audit 1
| Tuesday, August 09, 2016 | 1.Created Project DSDM Project Roles Summary
| Wednesday, August 10, 2016 | 1.Prepared and reviewed all documents(including project proposal, gantt chart, team contract and client brief document) 2.Held the advisor meeting with Steve 3.Held the meeting with Robert | Project proposal has not been completed and it has already behind the planning schedule as we had stated the reason of the weekly progress report - week 5. We changed the methodology to DSDM. Therefore, we were have to do the research for DSDM to understand the context and progress of it. As we estimated we have behind the planned schedule one week. We will use the fast tracking to do more things in the same time in order to catch up the behind schedule.
| Thursday, August 11, 2016 | 1.Created advisor meeting minutes 2.Edited documents with the suggestion of Steve and Robert
Friday, August 12, 2016
Saturday, August 13, 2016
| Sunday, August 14, 2016 | 1.Held team meeting 2.Created team meeting minutes 3.Reviewed the documents for project audit 1 | Created weekly report - week 5, explain the reason of why the project team has behind the planned schedule.
6 | Monday, August 15, 2016 | 1.Created advisor meeting agenda 2.Created progress report for advisor meeting 3.Created and completed the Project DSDM Terms of Reference 4.Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App)
| Tuesday, August 16, 2016 | 1.Held advisor meeting 2.Created advisor meeting minutes 3.Edited and completed Gantt Chart 4.Completed Progress Report for Project Audit 1 5.Drafted Requirements Analysis document 6.Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App)
| Wednesday, August 17, 2016 | Project Admin : Create Supporting Documents - prepare the documents for Project Audit 1 Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App) Project Audit : Project Audit 1 Reflection and summary after Project Audit 1 Analysis and Design Documents : Website Analysis and Design Document Project Admin : Personal Logs Project Admin : Timesheet Project Admin : Project Diary | Project Audit 1 Issues: advisor meeting - lack of meeting agenda - miss a couple of standrad items miniutes - follow agend exactly 1:1 progress report - lack of report, create weekly progress report, should include per hour, per tasks take by person time card - behind the planned schedule documents - signed and original documents need to be separated, backup all documents and test the backup version ensure it work
| Thursday, August 18, 2016 | Project Admin : Create Supporting Documents -- Requirements analysis document Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet Project Admin : Create Supporting Documents -- Team meeting agenda
| Friday, August 19, 2016 | Project Admin : Create Supporting Documents -- Requirements analysis document Analysis and Design Documents : Website Analysis and Design Document Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet Project Admin : Create Supporting Documents -- Team meeting agenda
| Saturday, August 20, 2016 | Project Admin : Create Supporting Documents -- Requirements analysis document Analysis and Design Documents : Website Analysis and Design Document Analysis and Design Documents : Database Evaluator Analysis and Design Document Project Admin : Personal Logs Project Admin : Timesheet Project Admin : Project Diary
| Sunday, August 21, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 6) Analysis and Design Documents : Database Evaluator Analysis and Design Document Analysis and Design Documents : Website Analysis and Design Document Exploration Phase : Iteration Two : Website : Program the Register Form Project Admin : Create Supporting Documents - Edit Grantt Chart Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | Edit Grantt Chart: edit the Actual start and finish date will change the start and finish time Solution: Set the project plan as baseline and then use the Baseline Start/Finish fields for comparison with the schedule. Then add the Actual start and finish date.
7 | Monday, August 22, 2016 | Project Admin : Create Supporting Documents - Team meeting agenda Project Admin : Create Supporting Documents - Project DSDM Terms of Reference Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Analysis and Design Documents : Website Analysis and Design Document Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet
| Tuesday, August 23, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Project Admin : Create Supporting Documents - DeliveryApproachDefinition Pre-project, Feasibility and Foundation : Requirements Analysis Analysis and Design Documents : Database Evaluator Analysis and Design Document Exploration Phase : Iteration Two : Website : Program the Register Form Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | We were confused on the different between the Requirements analysis document and System analysis and design document. We discussed this question with Steve during the advisor meeting. He gave us some ideas of the different between the Requirements analysis document and System analysis and design document. The Requirements analysis document is focused on the what the project is going to do. And the System analysis and design document is more focused on the how to achieve the requirements, how to do the functions of the project. Research References: System Architecture Sample: https://www.google.co.nz/url?sa=t&rct=j&q=&esrc=s&source=web&cd=1&ved=0ahUKEwio__TT0dbOAhWIppQKHT0iDrkQFggaMAA&url=http%3A%2F%2Fblog.cm-dm.com%2Fpublic%2FTemplates%2Fsystem-architecture-template.doc&usg=AFQjCNEoJqOU73TMuOkSwGibLHQwy3KzLA&sig2=7eamJa-5iXJjlebsGLTuxA&bvm=bv.129759880,d.dGo&cad=rja http://www.gs1.org/sites/default/files/docs/architecture/GS1_System_Architecture.pdf https://www.google.co.nz/url?sa=t&rct=j&q=&esrc=s&source=web&cd=2&cad=rja&uact=8&ved=0ahUKEwikz5L21tbOAhUBrJQKHaxuC9kQFggiMAE&url=http%3A%2F%2Fcse.hcmut.edu.vn%2F~minhnnn%2FFile%2FDocument%2FSE%2FSEPr2%2FExamples%2FSAD-OnlineCateringService.doc&usg=AFQjCNHUJdAeHFIFReW9ghsr7Jt8ZNfiKw&sig2=7Y-dCGUWJ4ARFS3n4Ixkaw https://oce.jpl.nasa.gov/practices/dfe6.pdf
| Wednesday, August 24, 2016 | Project Admin : Create Supporting Documents - DeliveryApproachDefinition Project Admin : Create Supporting Documents - ManagementFoundations Pre-project, Feasibility and Foundation : Requirements Analysis Analysis and Design Documents : Database Evaluator Analysis and Design Document Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test Exploration Phase : Iteration Two : Website : Program the Register Form Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | Requirements Analysis Research References: Creating Tables in PDF http://www.mikesdotnetting.com/article/86/itextsharp-introducing-tables http://stackoverflow.com/questions/2321526/pdfptable-as-a-header-in-itextsharp StringEncryption: https://dotnetfiddle.net/bFvxp8 http://stackoverflow.com/questions/22466858/decryption-exception-length-of-the-data-to-decrypt-is-invalid http://stackoverflow.com/questions/2919228/specified-key-is-not-a-valid-size-for-this-algorithm Creating Tables in PDF http://stackoverflow.com/questions/9417054/itextsharp-set-table-cell-border-color http://stackoverflow.com/questions/5806242/define-foreground-color-of-a-itextsharp-table-cell/5806603
| Thursday, August 25, 2016 | Project Admin : Create Supporting Documents - ManagementFoundations Project Admin : Create Supporting Documents - Team meeting agenda Analysis and Design Documents : Database Evaluator Analysis and Design Document Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test Analysis and Design Documents : Website Analysis and Design Document Project Admin : Project Diary Project Admin : Timesheet | Research References: Splash Screen https://msdn.microsoft.com/en-us/library/system.windows.forms.control.mousedown(v=vs.110).aspx http://stackoverflow.com/questions/1592876/make-a-borderless-form-movable http://stackoverflow.com/questions/7482922/remove-the-title-bar-in-windows-forms Visual Studio Issue with Debugger http://stackoverflow.com/questions/8311303/cannot-obtain-value-of-local-or-argument-as-it-is-not-available-at-this-instruct Get SQL Server Print Messages http://stackoverflow.com/questions/1880471/capture-stored-procedure-print-output-in-net
| Friday, August 26, 2016 | Project Admin : Create Supporting Documents - OutlinePlan Analysis and Design Documents : Database Evaluator Analysis and Design Document Analysis and Design Documents : Website Analysis and Design Document Project Admin : Timesheet | Research References: Write to File C# https://msdn.microsoft.com/en-us/library/8bh11f1k.aspx Read from file https://msdn.microsoft.com/en-us/library/ezwyzy7b.aspx Write Byte to File http://stackoverflow.com/questions/6397235/write-bytes-to-file Read byte from file August http://stackoverflow.com/questions/2030847/best-way-to-read-a-large-file-into-a-byte-array-in-c XML to string http://stackoverflow.com/questions/963870/dataset-writexml-to-string
| Saturday, August 27, 2016 | Project Admin : Create Supporting Documents - OutlinePlan Exploration Phase : Iteration Two : Submit Test Report Iteration Two (.exe App) Analysis and Design Documents : Website Analysis and Design Document Project Admin : Timesheet
| Sunday, August 28, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 7) Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | We did the project smoothly in week 7 and we were nearly to catch the planning schedule. As we reported in Weekly Progress Report - Week 5. We were behind the planning schedule. In week 6 and 7, we used the fast tracking to do some tasks as same time. Therefore, we estimate we can totally catch up the planning schedule at the end of week 8. Research References: Minimize C# Form https://msdn.microsoft.com/en-us/library/system.windows.forms.form.minimizebox%28v=vs.110%29.aspx Icons for GUI http://www.flaticon.com Progress Bar http://stackoverflow.com/questions/312936/windows-forms-progressbar-easiest-way-to-start-stop-marquee
8 | Monday, August 29, 2016 | Project Admin : Create Supporting Documents - Pre-Project Phase Tasks and Milestones Signoff Project Admin : Create Supporting Documents - BusinessFoundations SQL Server R&D WordPress R&D Exploration Phase : Iteration Two : Website : Verification of the Customer Email Address Exploration Phase : Iteration Three : exe App : Completely Working GUI Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | Research References: Restrict Multiple Instances: http://stackoverflow.com/questions/1207105/restrict-multiple-instances-of-an-application Close an Application: https://social.msdn.microsoft.com/Forums/windows/en-US/13e34c62-52c7-45b3-8bb4-16d9574d76be/how-to-close-c-form?forum=winforms Change Application Icon: https://msdn.microsoft.com/en-us/library/339stzf7.aspx
| Tuesday, August 30, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Project Admin : Create Supporting Documents - BusinessFoundations SQL Server R&D WordPress R&D Exploration Phase : Iteration Two : Website : Basic Account User Page Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing Project Admin : Project Diary Project Admin : Personal Logs Project Admin : Timesheet | Requirements Analysis Document and System Analysis and Design Document did not include any specified detail about exactly what the project is going to do. These should have the description of the following questiong: What parameter will be analysed? How and what the parameter is going to be? What adjustment of this project is going to make about parameter? What’s the report based on the parameter? The main things of the product are going to do should be explained clearly in the document.
| Wednesday, August 31, 2016 | Project Admin : Create Supporting Documents -- Team meeting agenda Project Admin : Create Supporting Documents - BusinessAreaDefinition WordPress R&D Exploration Phase : Iteration Two : Website : Program the Login Form Exploration Phase : Iteration Three : exe App : Encrypted Dumpfile with Testing Project Admin : Personal Logs Project Admin : Timesheet
| Thursday, September 01, 2016 | Analysis and Design Documents : Database Evaluator Analysis and Design Document WordPress R&D Exploration Phase : Iteration Three : exe App : Completely Working GUI Project Admin : Timesheet | Research References: Restore SQL Server DB: https://msdn.microsoft.com/en-us/library/ms177429%28SQL.90%29.aspx
| Friday, September 02, 2016 | Project Admin : Create Supporting Documents - BusinessAreaDefinition WordPress R&D Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing Project Admin : Personal Logs Project Admin : Timesheet
| Saturday, September 03, 2016 | Project Admin : Create Supporting Documents -- documents for project audit 2 Analysis and Design Documents : Database Evaluator Analysis and Design Document SQL Server R&D Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) Project Admin : Personal Logs Project Admin : Timesheet
| Sunday, September 04, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 7) C# R&D Project Admin : Project Diary Project Admin : Timesheet | In week 8, project team still worked hard and did the project smoothly. We have already caught the planning schedule as we estimated last week. We were behind the planning schedule one week because the plenty changes of methodology and documents as we had explained in Weekly Progress Report - Week 5. However, through the continuous efforts of the project team, we used 3 weeks to catch up the behind schedule. We already finished the Iteration Three of Exploration Phase and totally caught the planning schedule.
9 | Monday, September 05, 2016 | Project Admin : Create Supporting Documents - Signoff Document of Foundation Phase Tasks and milestone Project Admin : Create Supporting Documents - BusinessFoundations Project Admin : Create Supporting Documents - Foundations - PrioritisedRequirementsList Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms WordPress R&D Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | Research References: Creating Sequence Diagrams: http://www.objectaid.com/
| Tuesday, September 06, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Project Admin : Create Supporting Documents - Foundations - PrioritisedRequirementsList Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | What the content should be included on the methodology and techniques document? Try to apply the methodology and show the copontion of methodology create the brief report of each iteration to explain the conten, tasks and status ( progress, well and unwell ) of this project phase. Research References: Using Notepad++: http://stackoverflow.com/questions/4675202/notepad-setting-for-disabling-auto-open-previous-files Undo Indentation Visual Studio: http://stackoverflow.com/questions/9012055/indentation-shortcuts-in-visual-studio Using Concatenate in Excel: https://www.ablebits.com/office-addins-blog/2015/07/15/excel-concatenate-strings-cells-columns/ SQL Formatter: http://www.dpriver.com/pp/sqlformat.htm Newline in C#: http://www.dotnetperls.com/newline Newline in C#
| Wednesday, September 07, 2016 | Project Admin : Create Supporting Documents -- Team meeting agenda Project Admin : Create Supporting Documents - Prepare the documents for Project Audit 2 SQL Server R&D Engineering : Iteration One : Website: Upload of Customer Parameters or PDF to Website Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | Progress table for Client Application still not working correctly but made some changes to make it partially working
| Thursday, September 08, 2016 | Project Admin : Create Supporting Documents - Closeout report for Pre-Project Phase SQL Server R&D Engineering : Iteration One : Website: Upload of Customer Parameters or PDF to Website
| Friday, September 09, 2016 | Project Admin : Create Supporting Documents - Closeout report for Pre-Project Phase Project Audit : Project Audit 2 Analysis and Design Documents : Database Evaluator Analysis and Design Document SQL Server R&D Engineering : Iteration One : Website: Forgot Password Function Page Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing
| Saturday, September 10, 2016 | Project Admin : Create Supporting Documents -- Closeout report for Pre-Project Phase Analysis and Design Documents : Database Evaluator Analysis and Design Document Engineering : Iteration One : Website: Forgot Password Function Page Submit Test Report Iteration One (.exe App) | Hardik requested to block evaluation of SQL Server newer than 2012 older than 2008 R2 so this feature has to be added
| Sunday, September 11, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 9) Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) Lecture Conflict Management and WordPress R&D C# R&D
10 | Monday, September 12, 2016 | Analysis and Design Documents : Database Evaluator Analysis and Design Document Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) Project Admin : Create Supporting Documents Engineering : Iteration Two : Website: Create Documentation Page Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing
| Tuesday, September 13, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Testing R&D Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing WordPress R&D Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | Discuss the content of User manual and confirm the responsibility of it - This document will focus on the following list: • Download software • Download zip file • How to install and setup the software • How the system requirement will be needed for setup and implementing and make it running
| Wednesday, September 14, 2016 | Project Admin : Create Supporting Documents -- Team meeting agenda SQL Server R&D Engineering : Iteration Two : Website: Add Plugins and Review all links Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | Hardik requested to update the UI of Client Application to make it more usable
| Thursday, September 15, 2016 | Project Admin : Create Supporting Documents -- System test plan SQL Server R&D Analysis and Design Documents : Database Evaluator Analysis and Design Document WordPress R&D | Update the system analysis and design document with the comment from project advisor. Add the DFD diagrams. Explain the description of screenshot. Add a data dictionary and more detail about what description will be stored. Discuss the content of User manual and confirm the responsibility of it
| Friday, September 16, 2016 | Project Admin : Create Supporting Documents -- Closeout report for Exploration Phase SQL Server R&D WordPress R&D Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing
| Saturday, September 17, 2016 | Project Admin : Create Supporting Documents -- Closeout report for Exploration Phase SQL Server R&D WordPress R&D Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | Hardik requested to update the formatting of the PDF Report Generated
| Sunday, September 18, 2016 | Project Admin : Create Supporting Documents -- System test plan Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 10) Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
11 | Monday, September 19, 2016 | Project Admin : Create Supporting Documents -- System test plan SQL Server R&D WordPress R&D Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
| Tuesday, September 20, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes SQL Server R&D WordPress R&D Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly | Hardik has more comments on PDF Formatting so this have to be updated Admin account how to upload the particular diagnosed file to particular user - Solution: a. Send an email to user instead to upload file b. Using the existing code to add the upload file function for solving this problem c. Create own code for upload file function for particular user
| Wednesday, September 21, 2016 | Project Admin : Create Supporting Documents -- System test case SQL Server R&D WordPress R&D Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
| Thursday, September 22, 2016 | Project Admin : Create Supporting Documents -- System test case SQL Server R&D Engineering : Iteration Three : Website : Notification Email for Customer and Developer Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
| Friday, September 23, 2016 | Project Admin : Create Supporting Documents -- System test case SQL Server R&D WordPress R&D Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
| Saturday, September 24, 2016 | Project Admin : Create Supporting Documents -- System test case SQL Server R&D WordPress R&D Engineering : Iteration Three : Submit Test Report Iteration Three (.exe App) | There is no code documentation yet so a Help File for it needs to be created
| Sunday, September 25, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Team Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 11) Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
12 | Monday, September 26, 2016 | Deployment : System Test : Perform and record test results for System Test SQL Server R&D WordPress R&D Deployment : Combine Website, Client Application and Database Evaluator | Do the research of
| Tuesday, September 27, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Deployment : System Test : Perform and record test results for System Test SQL Server R&D Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed Deployment : Combine Website, Client Application and Database Evaluator | Dashboard Page of Website • Administrator account How to upload the diagnosed report to the special user How to make the report make the particular file How to know which file has been generated the matching diagnosed report
| Wednesday, September 28, 2016 | Deployment : System Test : Perform and record test results for System Test Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes SQL Server R&D WordPress R&D
| Thursday, September 29, 2016 | Deployment : System Test : Perform and record test results for System Test Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
| Friday, September 30, 2016 | Deployment : System Test : Perform and record test results for System Test Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing WordPress R&D Deployment : System Test : Test Case for System Test
| Saturday, October 01, 2016 | Deployment : System Test : Perform and record test results for System Test Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing WordPress R&D
| Sunday, October 02, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Project Admin : Create Supporting Documents - Team Meeting agenda Project Admin : Create Supporting Documents - Weekly progress report (week 12) WordPress R&D
13 | Monday, October 03, 2016 | Deployment : Iteration Three: System Test Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed Deployment : Iteration Two: Fix issues for Iteration Two | The issue of uploding website Different structure between local and online server. Don’t automatically change the path when upload the website Cause some functions don’t work on the online server Then cause project team just did the system test using the local host webiste with client application and database evaluator. That will possibly make some risks with execute the application on user's system. Solution: Fix the uploading issues Increase test time (03/10/16 – 09/10/16) Add 2 more iterations for system test
| Tuesday, October 04, 2016 | Meeting : Weekly Meeting with Project Advisor Project Admin : Create Supporting Documents - Meeting minutes Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly WordPress R&D Deployment : Iteration Two: Fix issues for Iteration Three | Issues were found for the Client Application during testing and this have to be fixed
| Wednesday, October 05, 2016 | Project Admin : Create Supporting Documents - Signoff Document of Engineering Phase Tasks and milestone Project Admin : Create Supporting Documents - Closeout report for Engineering PhaseDeployment : Iteration Four: System Test Deployment : Iteration Three: Fix issues for Iteration Three Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
| Thursday, October 06, 2016 | Deployment : Iteration Four: System Test Deployment : Iteration Three: Fix issues for Iteration Three Engineering : Iteration Two : Website: Add Plugins and Review all links Deployment : Iteration Two: Fix issues for Iteration Four
| Friday, October 07, 2016 | Deployment : Iteration Four: System Test Deployment : Iteration Four: Fix issues for Iteration Four WordPress R&D Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
| Saturday, October 08, 2016 | Project Admin : Create Supporting Documents - Team Meeting agenda Deployment : Iteration Four: Fix issues for Iteration Four WordPress R&D Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
| Sunday, October 09, 2016 | Project Admin : Create Supporting Documents - Advisor Meeting agenda Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Project Admin : Create Supporting Documents - Weekly progress report (week 13) WordPress R&D
14 | Monday, October 10, 2016 | Deployment : Create System test report Post Project : Create Project Close out Report Post Project : Create Individual Report
| Tuesday, October 11, 2016 | Post Project : Create Project Close out Report Meeting : Consulting Robert For Documents Review Post Project : Collating Documents Post Project : Create Individual Report
| Wednesday, October 12, 2016 | Post Project : Create Project Close out Report Post Project : Create Individual Report
| Thursday, October 13, 2016 | Post Project : Create Individual Report
| Friday, October 14, 2016 | Post Project : Create Individual Report
| Saturday, October 15, 2016 | Post Project : Create Individual Report
| Sunday, October 16, 2016 | Meeting : Frequent Face-to-Face Meeting with Team Members Project Admin : Create Supporting Documents - Team meeting minutes Project Admin : Create Supporting Documents - Weekly progress report (week 14)

## Project Tasks
Task Name | Comments
Pre-project, Feasibility and Foundation : Initial Plan
Pre-project, Feasibility and Foundation : Project Proposal
Pre-project, Feasibility and Foundation : Scope of Project
Pre-project, Feasibility and Foundation : Requirements Analysis
Pre-project, Feasibility and Foundation : Research Methodology
Pre-project, Feasibility and Foundation : Select Methodology
Pre-project, Feasibility and Foundation : Project Gantt Chart
Pre-project, Feasibility and Foundation : Meet Project Advisor
Pre-project, Feasibility and Foundation : Meet Co-ordinator
Pre-project, Feasibility and Foundation : Co-ordinator Approval
Pre-project, Feasibility and Foundation : Complete Project Proposal
Pre-project, Feasibility and Foundation : Complete Gantt Chart
Analysis and Design Documents : Website Analysis and Design Document
Analysis and Design Documents : Client Application Analysis and Design Document
Analysis and Design Documents : Database Evaluator Analysis and Design Document
Exploration Phase : Iteration One : Website : Plan Website and Choose Wordpress Template
Exploration Phase : Iteration One : Submit Test Report Iteration One (Website)
Exploration Phase : Iteration One : exe App: Client Application Design
Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App)
Exploration Phase : Iteration Two : Website : Program the Register Form
Exploration Phase : Iteration Two : Website : Program the Login Form
Exploration Phase : Iteration Two : Website : Verification of the Customer Email Address
Exploration Phase : Iteration Two : Website : Basic Account User Page
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (Website)
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (.exe App)
Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website
Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (Website)
Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server
Exploration Phase : Iteration Three : exe App : Completely Working GUI
Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing
Exploration Phase : Iteration Three : exe App : Encrypted Dumpfile with Testing
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App)
Engineering : Iteration One : Website: Upload of Customer Parameters or PDF to Website
Engineering : Iteration One : Website: Forgot Password Function Page
Engineering : Iteration One : Submit Test Report Iteration One (Website)
Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing
Engineering : Iteration One : Submit Test Report Iteration One (.exe App)
Engineering : Iteration Two : Website: Create Documentation Page
Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
Engineering : Iteration Two : Website: Add Plugins and Review all links
Engineering : Iteration Two : Submit Test Report Iteration Two (Website)
Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing
Engineering : Iteration Two : Submit Test Report Iteration Two (.exe App)
Engineering : Iteration Three : Website : Notification Email for Customer and Developer
Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
Engineering : Iteration Three : Submit Test Report Iteration Three (Website)
Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
Engineering : Iteration Three : Submit Test Report Iteration Three (.exe App)
Deployment : Combine Website, Client Application and Database Evaluator
System Test : Test Plan for System Test
System Test : Test Case for System Test
System Test : Test Results for System Test
System Test : Check all the Phases If all Requirements were Delivered
Post Project : Review Project
Post Project : Collating Documents
Project Admin : Project Diary
Project Admin : Personal Logs
Project Admin : Timesheet
Project Admin : Create Supporting Documents
Meeting : Frequent Face-to-Face Meeting with Team Members
Meeting : Weekly Meeting with Project Advisor
Meeting : Consulting Robert For Documents Review
Project Audit : Project Audit 1
Project Audit : Project Audit 2
Presentation Preparation : Project Presentation
C# R&D
SQL Server R&D | Building SQL Server Scripts and Test
WordPress R&D
Absent : Sick Leave