## Document History
Date | Sheet | Change | Modified By | Description | Comments | Version
2016-05-11 | PriceCompare Test Plan | - | Patrick Cura | Initial document created | - | 1

## PriceCompare Test Plan
Database Evaluator Website Test Plan
Tester Details
Description | Project: Database Evaluator Website
Tester's Name | Kwinno Pineda
Date for Iteration | 15/08/16 – 26/08/16
Status Summary
Test Summary | [5 empty] | 14.55%
General Detailed Checking
Application | Grouping | Function | Details | Y/N | Tester's Comments
Website | Program Register Form | Wordpress Register Validation | Validation Working but need more test to test to checked quality of it. | Y
| Program Register Form | Submission of the Registration | Working submission of register | N
|  | Record to database | Filled values recorded to database | Y | Not done
|  | Send email notification | send email notification after Registration | Y | Not done
|  | Activation key of email notification | Activation key receive to confirm Registration | Y | Not done
| Program Login Form or Page | Login as subscriber | Login as subscriber working now | N | need to fix some error
|  | Login as Administrator | Login as subscriber working now | N | need to fix some error
|  | Strong Password | Strong password combination of Uppercase, lowercase, number and special character | Y
|  | Match Password | passsword will be match according to the registered user on the database, validation if null or doesnt have a match to the user | Y
|  | Match Username | username unique can use username of email to login in | Y
| Verification of the email address | Send email notification | after registration automatic email will be sent to verify that the users email is active | N | working in locahost thinking if it will work at live web
|  | Activation key of email notification | Activation key receive to confirm Registration | Y
| Basic Account User Page | Subscriber Page | Page Report of the download and upload by the subscriber | N | nearly done
Note on F9: If NO, please attach screenshot of the error.

## Options
Y
N