## Document History
Date | Sheet | Change | Modified By | Description | Comments | Version
2016-08-01 | Test Plan | - | Patrick Cura | Initial document created | - | 1

## Test Plan
Test Plan
Tester Details
Description | Test Results for the Database Evaluator Project
Tester's Name | Patrick Ian E. Cura
Date checked | Week of August 28 to September 3, 2016
Status Summary
Test Summary | [5 empty] | 100%
General Detailed Checking
Application | Grouping | Function | Details | Y/N | Tester's Comments
Client Application | Splash Screen | Display Waiting Screen | At the start, a Splash Screen is displayed with a loading bar | Y
|  |  | Splash screen has no close button | Y
|  |  | Splash screen is draggable | Y
|  |  | Splash screen is not resizable | Y
| Main Screen | Server Dropdown Box | List of SQL Server instances appear | Y | Sometimes nothing appears
|  |  | User can manually type in server instance | Y
|  |  | Editing the dropdown box disables the Database check box, dropdown and progress area. | Y
|  | Check Server Connection | Manually changing the Server name then pressing enter initiates a connection check. A Green Check is shown if it is successful. A Red Mark is shown if it is not. A connection check is also initiated when choosing from one of the choices in the server dropdown. | Y
|  |  | If the server check takes time the progress bar below is enabled and the Form elements are not clickable while processing is ongoing via threading. | Y
|  |  | Pop-up is shown when connection is not successful | Y
|  | Database Checkbox | Database checkbox becomes enabled after successful server connection | Y
|  |  | When ticked, database dropdown and progress table is enabled | Y
|  |  | When not ticked, database dropdown and progress table becomes disabled | Y
|  | Database Dropdown Box | The dropdown box is filled with the databases under the selected instance | Y
|  | Start Button | When clicked, the start button is disabled and progress is displayed in the progress tables | Y
|  |  | When clicked the processing starts and after a while the user is asked where to save the dump file. The dump file is also encrypted. | Y
|  | Main Screen | Application is not resizable | Y
Database Evaluator | Main Screen | Browse Button | Clicking the browse button opens a dialog box wherein you can choose the dump file | Y
|  |  | When a file is selected, the path to the file is displayed in the Path to XML text box | Y
|  | Start Button | Clicking on the start button starts the decryption of the xml file and produces a PDF report. User is asked where to save the PDF file after the processing | Y
Note on F9: If NO, please attach screenshot of the error.

## Options
Y
N