## Summary
Week | Date | Changming Wu | Hardik Kansara | Kwinno Pineda | Patrick Cura | Weekly Total Hours
1 | 11/07/16 - 17/07/16 | 25 | 21 | 26 | 27 | 99
2 | 18/07/16 - 24/07/16 | 26 | 22 | 26 | 21 | 95
3 | 25/07/16 - 31/07/16 | 27 | 24 | 30 | 30 | 111
4 | 01/08/16 - 07/08/16 | 24 | 22 | 27.5 | 28 | 101.5
5 | 08/08/16 - 14/08/16 | 25 | 23 | 24 | 28 | 100
6 | 15/08/16 - 21/08/16 | 42.5 | 42 | 34 | 32 | 150.5
7 | 22/08/16 - 28/08/16 | 41.5 | 42 | 36.5 | 33 | 153
8 | 29/08/16 - 04/09/16 | 38.5 | 38 | 32.5 | 42 | 151
9 | 05/09/16 - 11/09/16 | 0 | 38.5 | 17.5 | 24 | 80
10 | 12/09/16 - 18/09/16 | 0 | 38 | 0 | 0 | 38
11 | 19/09/16 - 25/09/16 | 0 | 35 | 0 | 0 | 35
12 | 26/09/16 - 02/10/16 | 0 | 32 | 0 | 0 | 32
13 | 03/10/16 - 09/10/16 | 0 | 0 | 0 | 0 | 0
14 | 10/10/16 - 16/10/16 | 0 | 0 | 0 | 0 | 0
|  | 249.5 | 377.5 | 254 | 265 | 1146

## Changming Wu
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Project Proposal | 12:00 pm - 04:00 pm | 4 | 25
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-07-12 | Pre-project, Feasibility and Foundation : Project Proposal | 12:00 pm - 04:00 pm | 4
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-07-13 | Pre-project, Feasibility and Foundation : Research Methodology | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-14 | Pre-project, Feasibility and Foundation : Project Proposal | 04:00 pm - 06:00 pm | 2
|  | Project Admin : Project Diary | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
2016-07-15
| 2016-07-16 | Pre-project, Feasibility and Foundation : Project Proposal | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-17 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Project Proposal | 10:30 am - 11:30 am | 1 | 26
|  | Pre-project, Feasibility and Foundation : Project Gantt Chart | 11:30 am - 03:30 pm | 4
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-19 | Pre-project, Feasibility and Foundation : Project Proposal (update project plan) | 11:00 am - 12:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal (Create personal CV) | 01:00 pm - 02:00 pm | 1
|  | Pre-project, Feasibility and Foundation : Project Proposal (update Spiral Model ) | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-20 | Pre-project, Feasibility and Foundation : Project Proposal | 11:30 am - 01:30 pm | 2
|  | Meeting : Consulting Robert For Documents Review | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 1
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-07-21 | Project Admin : Create Supporting Documents - team meeting agenda | 12:30 pm - 01:00 pm | 0.5
|  | Project Admin : Create Supporting Documents - project management plan | 09:00 am - 10:00 am 04:00 pm - 06:30 pm | 3.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
2016-07-22
| 2016-07-23 | Pre-project, Feasibility and Foundation : Project Proposal | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-07-24 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Project Admin : Create Supporting Documents -project proposal | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm -04:30 pm | 0.5
3 | 2016-07-25 | Project Admin : Create Supporting Documents -client brief document | 10:30 am - 03:30 pm | 5 | 27
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
| 2016-07-26 | Pre-project, Feasibility and Foundation - DSDM Model | 10:30 am - 02:30 pm | 4
|  | Project Admin : Project Diary | 02:30 pm - 03:00 pm | 0.5
|  | Project Admin : Personal Logs | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
| 2016-07-27 | Project Admin : Create Supporting Documents -Created team contract | 12:00 pm - 05:00 pm | 5
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
2016-07-28
2016-07-29
| 2016-07-30 | Project Admin : Create Supporting Documents - communication plan | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
| 2016-07-31 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 01:00 pm -02:00 pm | 1
|  | Project Admin : Create Supporting Documents -the product assumption with DSDM | 02:00 pm - 03:30 pm | 1.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm -04:30 pm | 0.5
4 | 2016-08-01 | Project Admin : Create Supporting Documents - advisor meeting agenda | 12:00 pm - 01:00 pm | 1 | 24
|  | Project Admin : Create Supporting Documents - project anaylsis | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-02 | Project Admin : Create Supporting Documents - project time sheet template | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - project anaylsis and system outline | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05: 30 pm | 0.5
| 2016-08-03 | Project Admin : Create Supporting Documents - Analysis and Design Documents | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05: 30 pm | 0.5
2016-08-04
2016-08-05
| 2016-08-06 | Project Admin : Create Supporting Documents - Analysis and Design Documents | 01:00 pm - 03:00 pm | 2
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - list and confirm all documents all documents ofr project audit 1 | 01:00 pm - 03:30 pm | 1
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
5 | 2016-08-08 | Project Admin : Create Supporting Documents - data flow diagram and activity diagram | 11:00 am - 01:00 pm | 2 | 25
|  | Project Admin : Create Supporting Documents - Draft progress report for project audit 1 | 01:00 pm - 02:00 pm | 1
|  | Project Admin : Project Diary | 02:00 pm - 02:30 pm | 0.5
|  | Project Admin : Timesheet | 02:30 pm - 03:00 pm | 0.5
| 2016-08-09 | Project Admin : Create Supporting Documents - Project DSDM Project Roles Summary | 10:30 am - 04:30 pm | 5
|  | Project Admin : Project Diary | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Personal Logs | 05:00 pm - 05:30 pm | 0.5
| 2016-08-10 | Project Admin : Create Supporting Documents - Edit Gantt Chart | 11:30 am - 01:00 pm | 1.5
|  | Meeting : Weekly Meeting with Project Advisor | 03:00 pm - 04:00 pm | 1
|  | Meeting : Consulting Robert For Documents Review | 04:00 pm - 05:00 pm | 1
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
| 2016-08-11 | Project Admin : Create Supporting Documents - Meeting minutes | 12:30 pm - 01:30 pm | 1
2016-08-12
| 2016-08-13 | Project Admin : Create Supporting Documents - Review the documents for project audit 1 | 01:00 pm - 03:30 pm | 2.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-08-14 | Meeting : Frequent Face-to-Face Meeting with Team Members | 11:00 am - 12:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Review the documents for project audit 1 | 01:00 pm - 03:30 pm | 2.5
|  | Project Admin : Project Diary | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Personal Logs | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
6 | 2016-08-15 | Project Admin : Create Supporting Documents - advisor meeting agenda | 10:30 am - 11:00 am | 0.5 | 42.5
|  | Project Admin : Create Supporting Documents - Project DSDM Terms of Reference | 11:00 am - 05:00 pm | 6
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:50 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-16 | Meeting : Weekly Meeting with Project Advisor | 11:00 am - 11:30 pm | 0.5
|  | Project Admin : Create Supporting Documents - Meeting minutes | 11:30 am - 12:30 pm | 1
|  | Project Admin : Create Supporting Documents - Edit Gantt Chart | 12:30 pm - 04:30 pm | 4
|  | Project Admin : Create Supporting Documents - Complete Progress Report for Project Audit 1 | 04:30 pm - 05:30 pm | 1
|  | Project Admin : Project Diary | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Personal Logs | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
| 2016-08-17 | Project Admin : Create Supporting Documents - prepare the documents for Project Audit 1 | 11:30 am - 02:30 pm | 3
|  | Project Audit : Project Audit 1 | 03:00 pm - 04:00 pm | 1
|  | Reflection and summary after Project Audit 1 | 04:00 pm - 06:00 pm | 2
|  | Project Admin : Personal Logs | 06:00 pm - 06:30 pm | 0.5
|  | Project Admin : Timesheet | 06:30 pm - 07:00 pm | 0.5
|  | Project Admin : Project Diary | 07:00 pm - 07:30 pm | 0.5
| 2016-08-18 | Project Admin : Create Supporting Documents -- Requirements analysis document | 12:00 pm - 02:00 pm | 2
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Create Supporting Documents -- Team meeting agenda | 06:00 pm - 07:00 pm | 1
| 2016-08-19 | Project Admin : Create Supporting Documents -- Requirements analysis document | 01:00 pm - 04:00 pm | 3
|  | Project Admin : Project Diary | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-08-20 | Project Admin : Create Supporting Documents -- Requirements analysis document | 01:00 pm - 04:00 pm | 3
|  | Project Admin : Personal Logs | 04:00 pm -04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
| 2016-08-21 | Project Admin : Create Supporting Documents - Advisor Meeting agenda | 10:30 am - 11:30 am | 1
|  | Project Admin : Create Supporting Documents - Weekly progress report (week 6) | 11:30 am - 01:30 pm | 2
|  | Project Admin : Create Supporting Documents - Edit Grantt Chart | 01:30 pm - 02:30 pm | 1
|  | Project Admin : Project Diary | 02:30 pm - 03:00 pm | 0.5
|  | Project Admin : Personal Logs | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
7 | 2016-08-22 | Project Admin : Create Supporting Documents - Team meeting agenda | 10:30 am - 11:00 am | 0.5 | 41.5
|  | Project Admin : Create Supporting Documents - Project DSDM Terms of Reference | 11:00 am - 02:00 pm | 3
|  | Meeting : Frequent Face-to-Face Meeting with Team Members | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 03:00 pm - 04:00 pm | 1
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-08-23 | Meeting : Weekly Meeting with Project Advisor | 11:00 am - 11:30 pm | 0.5
|  | Project Admin : Create Supporting Documents - Meeting minutes | 11:30 am - 12:30 pm | 1
|  | Project Admin : Create Supporting Documents - DeliveryApproachDefinition | 01:00 pm - 04:00 pm | 3
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-08-24 | Project Admin : Create Supporting Documents - DeliveryApproachDefinition | 10:30 am - 02: 00 pm | 3.5
|  | Project Admin : Create Supporting Documents - ManagementFoundations | 02:00 pm - 05:00 pm | 3
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-08-25 | Project Admin : Create Supporting Documents - ManagementFoundations | 10:30 am - 03:30 pm | 5
|  | Project Admin : Create Supporting Documents - Team meeting agenda | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Project Diary | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-08-26 | Project Admin : Create Supporting Documents - OutlinePlan | 10:30 pm - 03:30 pm | 5
|  | Project Admin : Timesheet | 03:30 pm - 04:00 pm | 0.5
| 2016-08-27 | Project Admin : Create Supporting Documents - OutlinePlan | 12:00 pm - 03:00 pm | 3
|  | Project Admin : Timesheet | 03:00 pm - 03:30 pm | 0.5
| 2016-08-28 | Project Admin : Create Supporting Documents - Advisor Meeting agenda | 11:00 am - 11:30 am | 0.5
|  | Project Admin : Create Supporting Documents - Weekly progress report (week 7) | 11:30 am - 12:30 pm | 1
|  | Meeting : Frequent Face-to-Face Meeting with Team Members | 01:00 pm - 02:00 pm | 1
|  | Project Admin : Create Supporting Documents - Team meeting minutes | 02:00 pm - 03:00 pm | 1
|  | Project Admin : Project Diary | 03:00 pm - 03:30 pm | 0.5
|  | Project Admin : Personal Logs | 03:30 pm - 04:00 pm | 0.5
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
8 | 2016-08-29 | Project Admin : Create Supporting Documents - Pre-Project Phase Tasks and Milestones Signoff | 10:30 am - 12:30 pm | 2 | 38.5
|  | Project Admin : Create Supporting Documents - BusinessFoundations | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-30 | Meeting : Weekly Meeting with Project Advisor | 11:00 am - 11:30 am | 0.5
|  | Project Admin : Create Supporting Documents - Meeting minutes | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - BusinessFoundations | 01:00 pm - 05:00 pm | 4
|  | Project Admin : Project Diary | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Personal Logs | 05:30 pm - 06:00 pm | 0.5
|  | Project Admin : Timesheet | 06:00 pm - 06:30 pm | 0.5
| 2016-08-31 | Project Admin : Create Supporting Documents -- Team meeting agenda | 10:30 am - 11:30 am | 1
|  | Project Admin : Create Supporting Documents - BusinessAreaDefinition | 12:00 pm - 05:00 pm | 5
|  | Project Admin : Personal Logs | 05:00 pm - 05:30 pm | 0.5
|  | Project Admin : Timesheet | 05:30 pm - 06:00 pm | 0.5
| 2016-09-01 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 12:00 pm - 02:00 pm | 2
|  | Project Admin : Timesheet | 04:00 pm - 04:30 pm | 0.5
| 2016-09-02 | Project Admin : Create Supporting Documents - BusinessAreaDefinition | 11:00 am - 04:00 pm | 5
|  | Project Admin : Personal Logs | 04:00 pm - 04:30 pm | 0.5
|  | Project Admin : Timesheet | 04:30 pm - 05:00 pm | 0.5
| 2016-09-03 | Project Admin : Create Supporting Documents -- documents for project audit 2 | 12:00 pm - 03:00 pm | 3
|  | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 03:00 pm - 04:30 pm | 1.5
|  | Project Admin : Personal Logs | 04:30 pm - 05:00 pm | 0.5
|  | Project Admin : Timesheet | 05:00 pm - 05:30 pm | 0.5
| 2016-09-04 | Project Admin : Create Supporting Documents - Advisor Meeting agenda | 12:00 pm - 01:00 pm | 1
|  | Project Admin : Create Supporting Documents - Weekly progress report (week 7) | 01:00 pm - 02:00 pm | 1
|  | Project Admin : Project Diary | 02:00 pm - 02:30 pm | 0.5
|  | Project Admin : Timesheet | 02:30 pm - 03:00 pm | 0.5
9 | 2016-09-05 |  |  |  | 0
2016-09-06
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Hardik Kansara
Week | Date | Activity (Project Tasks) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Initial Plan |  | 2 | 21
| 2016-07-11 | Pre-project, Feasibility and Foundation : Requirements Analysis |  | 2
| 2016-07-12 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-13 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-14 | Pre-project, Feasibility and Foundation : Initial Plan |  | 2
| 2016-07-15 | Project Admin : Create Supporting Documents |  | 1
2016-07-16
| 2016-07-17 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-17 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-17 | Project Admin : Personal Logs |  | 0.5
| 2016-07-17 | Project Admin : Timesheet |  | 0.5
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Research Methodology |  | 5 | 22
| 2016-07-19 | Pre-project, Feasibility and Foundation : Research Methodology |  | 5
2016-07-20
| 2016-07-21 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 5
| 2016-07-22 | Pre-project, Feasibility and Foundation : Select Methodology |  | 3
| 2016-07-23 | Pre-project, Feasibility and Foundation : Select Methodology |  | 2
| 2016-07-24 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-24 | Project Admin : Personal Logs |  | 0.5
| 2016-07-24 | Project Admin : Timesheet |  | 0.5
3 | 2016-07-25 | Pre-project, Feasibility and Foundation : Project Proposal |  | 5 | 24
| 2016-07-26 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-26 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 1
| 2016-07-27 | SQL Server R&D |  | 4
| 2016-07-27 | Meeting : Consulting Robert For Documenets Review |  | 1
| 2016-07-28 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-29 | SQL Server R&D |  | 3
2016-07-30
| 2016-07-31 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-07-31 | Project Admin : Personal Logs |  | 0.5
| 2016-07-31 | Project Admin : Timesheet |  | 0.5
4 | 2016-08-01 | SQL Server R&D |  | 4 | 22
| 2016-08-02 | Pre-project, Feasibility and Foundation : Project Proposal |  | 5
| 2016-08-03 | Analysis and Design Documents : Database Evaluator Analysis and Design Document |  | 2
| 2016-08-04 | Analysis and Design Documents : Website Analysis and Design Document |  | 2
| 2016-08-05 | SQL Server R&D |  | 5
| 2016-08-06 | Analysis and Design Documents : Client Application Analysis and Design Document |  | 2
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members |  | 1
| 2016-08-07 | Project Admin : Personal Logs |  | 0.5
| 2016-08-07 | Project Admin : Timesheet |  | 0.5
5 | 2016-08-08 | Absent : Sick Leave |  |  | 23
| 2016-08-09 | Analysis and Design Documents : Client Application Analysis and Design Document |  | 4
| 2016-08-10 | Meeting : Weekly Meeting with Project Advisor |  | 0.5
| 2016-08-10 | Meeting : Consulting Robert For Documenets Review |  | 1
| 2016-08-10 | SQL Server R&D |  | 2
| 2016-08-10 | Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test |  | 2.5
2016-08-11
| 2016-08-12 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-08-13 | Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test |  | 4
| 2016-08-14 | SQL Server R&D |  | 5
6 | 2016-08-15 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6 | 42
| 2016-08-16 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:30 AM to 5:00 PM | 5.5
| 2016-08-16 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-08-17 | Project Audit : Project Audit 1 | 3:00 PM to 4:00 PM | 1
| 2016-08-17 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 3:00 PM | 4
| 2016-08-17 | Project Admin : Create Supporting Documents | 4:00 PM to 5:00 PM | 1
| 2016-08-18 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-19 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-20 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-21 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 3:00 PM | 4
| 2016-08-21 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-08-21 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
7 | 2016-08-22 | Project Admin : Create Supporting Documents | 11:00 AM to 2:00 PM | 3 | 42
| 2016-08-22 | Meeting : Frequent Face-to-Face Meeting with Team Members | 2:00 PM to 3:00 PM | 1
| 2016-08-22 | Project Admin : Create Supporting Documents | 3:00 PM to 5:00 PM | 2
| 2016-08-23 | Project Admin : Create Supporting Documents | 11:00 AM to 5:00 PM | 6
| 2016-08-24 | Project Admin : Create Supporting Documents | 11:00 AM to 2:00 PM | 3
| 2016-08-24 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 2:00 PM to 5:00 PM | 3
| 2016-08-25 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-26 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-27 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-08-28 | Project Admin : Create Supporting Documents | 11:00 AM to 3:00 PM | 4
| 2016-08-28 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-08-28 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
8 | 2016-08-29 | SQL Server R&D | 11:00 AM to 5:00 PM | 6 | 38
| 2016-08-30 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-08-30 | SQL Server R&D | 12:00 PM to 4:30 PM | 4.5
| 2016-08-31 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 5:00 PM | 6
| 2016-09-01 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 12:00 PM to 5:00 PM | 4.5
| 2016-09-02 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 12:00 PM to 5:00 PM | 4.5
| 2016-09-03 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-04 | Project Admin : Create Supporting Documents | 11:00 AM to 3:00 PM | 4
| 2016-09-04 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-09-04 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
9 | 2016-09-05 | Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server | 11:00 AM to 5:00 PM | 6 | 38.5
| 2016-09-06 | Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server | 11:00 AM to 5:00 PM | 6
| 2016-09-07 | SQL Server R&D | 11:00 AM to 4:00 PM | 5
| 2016-09-07 | Meeting : Frequent Face-to-Face Meeting with Team Members | 4:00 PM to 5:00 PM | 1
| 2016-09-08 | SQL Server R&D | 11:00 AM to 3:00 PM | 4
| 2016-09-09 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00 AM to 1:00 PM | 2
| 2016-09-09 | SQL Server R&D | 11:00 AM to 1:00 PM | 2
| 2016-09-10 | SQL Server R&D | 11:00 AM to 1:00 PM | 2
| 2016-09-10 | Project Audit : Project Audit 2 | 1:30 PM to 2:00 PM | 0.5
| 2016-09-10 | Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) | 11:00 AM to 3:00 PM | 4
| 2016-09-11 | Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) | 11:00 AM to 3:00 PM | 4
| 2016-09-11 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-09-11 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
10 | 2016-09-12 | Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) | 11:00 AM to 1:00 PM | 2 | 38
| 2016-09-12 | Project Admin : Create Supporting Documents | 1:00 PM to 5:00 PM | 4
| 2016-09-13 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-09-13 | Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | 11:30 AM to 4:00 PM | 4.5
| 2016-09-13 | Meeting : Frequent Face-to-Face Meeting with Team Members | 4:00 PM to 5:00 PM | 1
| 2016-09-14 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-15 | SQL Server R&D | 11:00 AM to 3:00 PM | 4
| 2016-09-15 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 3:00 PM to 5:00 PM | 2
| 2016-09-16 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-17 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-18 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-09-18 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
11 | 2016-09-19 | SQL Server R&D | 11:00 AM to 5:00 PM | 6 | 35
| 2016-09-20 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-09-20 | SQL Server R&D | 11:30 AM to 4:00 PM | 4.5
| 2016-09-20 | Meeting : Frequent Face-to-Face Meeting with Team Members | 4:00 PM to 5:00 PM | 1
| 2016-09-21 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-22 | SQL Server R&D | 11:00 AM to 4:00 PM | 5
| 2016-09-23 | SQL Server R&D | 11:00 AM to 4:00 PM | 5
| 2016-09-24 | SQL Server R&D | 12:00 PM to 3:00 PM | 3
| 2016-09-24 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 3:00 PM to 5:00 PM | 2
| 2016-09-25 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-09-25 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
12 | 2016-09-26 | SQL Server R&D | 11:00 AM to 5:00 PM | 6 | 32
| 2016-09-27 | Meeting : Weekly Meeting with Project Advisor | 11:00 AM to 11:30 AM | 0.5
| 2016-09-27 | SQL Server R&D | 11:30 AM to 4:00 PM | 4.5
| 2016-09-27 | Meeting : Frequent Face-to-Face Meeting with Team Members | 4:00 PM to 5:00 PM | 1
| 2016-09-28 | SQL Server R&D | 11:00 AM to 5:00 PM | 6
| 2016-09-29 | Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | 11:00 AM to 4:00 PM | 4
| 2016-09-30 | Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | 11:00 AM to 4:00 PM | 4
| 2016-10-01 | Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing | 11:00 AM to 4:00 PM | 4
| 2016-10-02 | Project Admin : Personal Logs | 3:00 PM to 4:00 PM | 1
| 2016-10-02 | Project Admin : Timesheet | 4:00 PM to 5:00 PM | 1
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Kwinno Pineda
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Initial Plan | 12:00pm – 5:00pm | 5 | 26
| 2016-07-12 | Pre-project, Feasibility and Foundation : Requirements Analysis | 10:30am – 4:00pm | 5.5
| 2016-07-13 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 9:00pm | 6
| 2016-07-14 | Pre-project, Feasibility and Foundation : Research Methodology | 2:00pm – 5:30pm | 3.5
| 2016-07-15 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 9:00pm | 6
2016-07-16
2016-07-17
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Research Methodology | 3:00pm – 4:00pm | 4 | 26
| 2016-07-19 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 7:30pm | 5
| 2016-07-20 | Meeting : Consulting Robert For Documenets Review | 2:00pm – 3:00pm | 1
| 2016-07-20 | Pre-project, Feasibility and Foundation : Select Methodology | 3:00pm – 9:00pm | 6
2016-07-21
| 2016-07-22 | Pre-project, Feasibility and Foundation : Select Methodology | 3:00pm – 9:00pm | 6
2016-07-23
| 2016-07-24 | Pre-project, Feasibility and Foundation : Select Methodology | 12:30pm – 4:30pm | 4
3 | 2016-07-25 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 09:30pm | 7 | 30
| 2016-07-26 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 9:00pm | 8
| 2016-07-27 | Pre-project, Feasibility and Foundation : Research Methodology | 1:30pm – 9:00pm | 7.5
2016-07-28
| 2016-07-29 | Pre-project, Feasibility and Foundation : Research Methodology | 5:00pm – 9:00pm | 4
2016-07-30
| 2016-07-31 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 4:30pm | 3.5
4 | 2016-08-01 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 5:00pm | 4 | 27.5
| 2016-08-02 | Pre-project, Feasibility and Foundation : Research Methodology | 12:30pm -5:00pm | 4.5
| 2016-08-03 | Analysis and Design Documents : Website Analysis and Design Document | 11:00am – 7:30pm | 8.5
2016-08-04
| 2016-08-05 | Pre-project, Feasibility and Foundation : Research Methodology | 4:00pm – 8:30pm | 4.5
2016-08-06
| 2016-08-07 | Meeting : Frequent Face-to-Face Meeting with Team Members | 10am-11:30am & 1pm -4:30pm | 6
5 | 2016-08-08 | Pre-project, Feasibility and Foundation : Research Methodology | 1:00pm – 8:00pm | 8 | 24
| 2016-08-09 | Pre-project, Feasibility and Foundation : Research Methodology | 2:00pm – 8:00pm | 6
| 2016-08-10 | Meeting with Steve then Robert | 1:00pm -5:00pm | 4
2016-08-11
| 2016-08-12 | Pre-project, Feasibility and Foundation : Research Methodology | 2:30pm – 4:30pm | 2
2016-08-13
| 2016-08-14 | Pre-project, Feasibility and Foundation : Project Gantt Chart | 2:30pm – 4:30pm | 4
6 | 2016-08-15 | Pre-project, Feasibility and Foundation : Project Gantt Chart | 10am-11am & 2:30pm – 10:00pm | 9 | 34
| 2016-08-16 | Project Admin : Timesheet, Project Admin : Personal Logs | 10:30am – 1pm & 3:00pm – 5:00pm | 4.5
| 2016-08-17 | Project Audit: Project Audit 1 | 3:00pm – 4:00pm | 1
| 2016-08-17 | Analysis and Design Documents : Website Analysis and Design Document | 12:30pm – 3:00pm | 2.5
| 2016-08-17 | Analysis and Design Documents : Website Analysis and Design Document | 4:00pm – 7:30pm | 3.5
| 2016-08-17 | Project Admin : Timesheet | 7:30pm – 8:00pm | 0.5
| 2016-08-17 | Project Admin : Personal Logs | 7:30pm – 8:00pm | 0.5
| 2016-08-18 | Absent : Sick Leave
| 2016-08-19 | Analysis and Design Documents : Website Analysis and Design Document | 2:00pm – 4:30pm | 2.5
| 2016-08-20 | Analysis and Design Documents : Website Analysis and Design Document | 9:00pm – 11:00pm | 2
| 2016-08-21 | Project Admin : Timesheet | 4:00pm – 4:30pm | 0.5
| 2016-08-21 | Project Admin : Personal Logs | 4:00pm – 4:30pm | 0.5
| 2016-08-21 | Exploration Phase : Iteration Two : Website : Program the Register Form | 12:30pm – 4:00pm | 3.5
| 2016-08-21 | Analysis and Design Documents : Website Analysis and Design Document | 12:30pm – 4:00pm | 3.5
7 | 2016-08-22 | Analysis and Design Documents : Website Analysis and Design Document | 2:00pm - 9:00pm | 7 | 36.5
| 2016-08-23 | Analysis and Design Documents : Website Analysis and Design Document | 5:00pm - 9:00pm | 4
| 2016-08-23 | Exploration Phase : Iteration Two : Website : Program the Register Form | 8:30am - 11:00pm | 2.5
| 2016-08-23 | Analysis and Design Documents : Database Evaluator Analysis and Design Document | 11:00pm - 5:00pm | 6
| 2016-08-24 | Meeting : Frequent Face-to-Face Meeting with Team Members | 1:00pm - 6:30pm | 5.5
| 2016-08-24 | Exploration Phase : Iteration Two : Website : Program the Register Form | 10:30pm - 2:00am | 3.5
| 2016-08-25 | Analysis and Design Documents : Website Analysis and Design Document | 2:00pm - 3:30pm | 1.5
| 2016-08-26 | Analysis and Design Documents : Website Analysis and Design Document | 9:00pm - 10:00pm | 1
| 2016-08-27 | Analysis and Design Documents : Website Analysis and Design Document | 11:00pm - 1:00am | 2
| 2016-08-28 | Meeting : Frequent Face-to-Face Meeting with Team Members | 12:00pm - 3:30pm | 3.5
8 | 2016-08-29 | WordPress R&D | 12:00pm - 3:00pm | 3 | 32.5
| 2016-08-29 | Exploration Phase : Iteration Two : Website : Verification of the Customer Email Address | 3:00pm - 7:30pm | 4.5
| 2016-08-30 | WordPress R&D | 11:00am - 4:00pm | 5
| 2016-08-30 | Exploration Phase : Iteration Two : Website : Basic Account User Page | 4:00pm - 8:00pm | 4
| 2016-08-31 | WordPress R&D | 12:00pm - 4:00pm | 4
| 2016-08-31 | Exploration Phase : Iteration Two : Website : Program the Login Form | 4:00pm - 8:00pm | 4
| 2016-09-01 | WordPress R&D | 11:00pm - 1:00am | 2
| 2016-09-02 | WordPress R&D | 3:00pm - 5:00pm | 2
| 2016-09-02 | Project Admin : Timesheet | 5:00pm - 6:00pm | 1
| 2016-09-02 | Project Admin : Personal Logs | 6:00pm - 7:30pm | 1.5
2016-09-03
| 2016-09-04 | WordPress R&D | 3:00pm - 4:30pm | 1.5
9 | 2016-09-05 | Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website | 12:00pm - 3:00pm | 3 | 17.5
| 2016-09-05 | Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms | 3:00pm - 6:00pm | 3
| 2016-09-05 | WordPress R&D | 6:00pm - 9:00pm | 3
| 2016-09-06 | Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website | 12:30pm - 4:00pm | 3.5
| 2016-09-06 | Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms | 4:00pm - 9:00pm | 5
2016-09-07
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Patrick Cura
Week | Date | Activity (Project activity code) | Period | Hours | Weekly Total Hors
1 | 2016-07-11 | Pre-project, Feasibility and Foundation : Initial Plan |  | 6 | 27
| 2016-07-12 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-12 | C# R&D |  | 4
| 2016-07-13 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4
| 2016-07-13 | C# R&D |  | 4
2016-07-14
2016-07-15
2016-07-16
| 2016-07-17 | C# R&D |  | 5
2 | 2016-07-18 | Pre-project, Feasibility and Foundation : Project Proposal |  | 4 | 21
| 2016-07-19 | C# R&D |  | 3
| 2016-07-19 | Pre-project, Feasibility and Foundation : Project Proposal |  | 3
| 2016-07-20 | C# R&D |  | 3
| 2016-07-20 | Pre-project, Feasibility and Foundation : Project Proposal |  | 3
2016-07-21
2016-07-22
| 2016-07-23 | C# R&D |  | 2
| 2016-07-24 | Pre-project, Feasibility and Foundation : Project Proposal |  | 3
3 | 2016-07-25 | C# R&D |  | 7 | 30
| 2016-07-26 | C# R&D |  | 7
| 2016-07-27 | C# R&D |  | 7
2016-07-28
2016-07-29
| 2016-07-30 | C# R&D |  | 4
| 2016-07-31 | C# R&D |  | 5
4 | 2016-08-01 | C# R&D |  | 3.5 | 28
| 2016-08-01 | Pre-project, Feasibility and Foundation : Requirements Analysis |  | 3.5
| 2016-08-02 | C# R&D |  | 5
| 2016-08-02 | Pre-project, Feasibility and Foundation : Requirements Analysis |  | 4
| 2016-08-03 | C# R&D |  | 6
2016-08-04
2016-08-05
2016-08-06
| 2016-08-07 | C# R&D |  | 6
5 | 2016-08-08 | Exploration Phase : Iteration One : exe App: Client Application Design |  | 6 | 28
| 2016-08-09 | C# R&D |  | 5
| 2016-08-10 | Meeting : Weekly Meeting with Project Advisor |  | 4
2016-08-11
2016-08-12
| 2016-08-13 | Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App) |  | 6
| 2016-08-14 | C# R&D |  | 7
6 | 2016-08-15 | Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App) |  | 8 | 32
| 2016-08-16 | Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App) |  | 8
| 2016-08-17 | Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App) |  | 8
| 2016-08-18 | Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test |  | 4
| 2016-08-19 | Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test |  | 4
2016-08-20
2016-08-21
7 | 2016-08-22 | Project Admin : Timesheet | 10:00 AM to 1:00 PM | 3 | 33
| 2016-08-22 | Analysis and Design Documents : Website Analysis and Design Document | 4:00 PM to 7:00 PM | 3
| 2016-08-23 | Pre-project, Feasibility and Foundation : Requirements Analysis | 11:00 AM to 8:00 PM | 9
| 2016-08-24 | Pre-project, Feasibility and Foundation : Requirements Analysis | 11:00 AM to 3:00 PM | 4
| 2016-08-24 | Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test | 5:00PM to 8:00 PM | 3
| 2016-08-25 | Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test | 6:00PM to 8:00 PM | 2
2016-08-26
| 2016-08-27 | Exploration Phase : Iteration Two : Submit Test Report Iteration Two (.exe App) | 1:00PM to 3:00PM | 2
| 2016-08-28 | Project Admin : Create Supporting Documents | 10:00AM to 5:00PM | 7
8 | 2016-08-29 | Exploration Phase : Iteration Three : exe App : Completely Working GUI | 1:00PM to 9:00PM | 8 | 42
| 2016-08-30 | Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing | 1:00PM to 9:00PM | 8
| 2016-08-31 | Exploration Phase : Iteration Three : exe App : Encrypted Dumpfile with Testing | 1:00PM to 9:00PM | 8
| 2016-09-01 | Exploration Phase : Iteration Three : exe App : Completely Working GUI | 6:00PM to 9:00PM | 3
| 2016-09-02 | Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing | 8:00PM to 11:00PM | 3
| 2016-09-03 | Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App) | 1:00PM to 7:00PM | 6
| 2016-09-04 | C# R&D | 2:00PM to 8:00PM | 6
9 | 2016-09-05 | Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | 1:00PM to 9:00PM | 8 | 24
| 2016-09-06 | Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | 2:00PM to 10:00PM | 8
| 2016-09-07 | Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing | 1:00PM to 9:00PM | 8
2016-09-08
2016-09-09
2016-09-10
2016-09-11
10 | 2016-09-12 |  |  |  | 0
2016-09-13
2016-09-14
2016-09-15
2016-09-16
2016-09-17
2016-09-18
11 | 2016-09-19 |  |  |  | 0
2016-09-20
2016-09-21
2016-09-22
2016-09-23
2016-09-24
2016-09-25
12 | 2016-09-26 |  |  |  | 0
2016-09-27
2016-09-28
2016-09-29
2016-09-30
2016-10-01
2016-10-02
13 | 2016-10-03 |  |  |  | 0
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
14 | 2016-10-10 |  |  |  | 0
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16

## Project Tasks
Task Name | Comments
Pre-project, Feasibility and Foundation : Initial Plan
Pre-project, Feasibility and Foundation : Project Proposal
Pre-project, Feasibility and Foundation : Scope of Project
Pre-project, Feasibility and Foundation : Requirements Analysis
Pre-project, Feasibility and Foundation : Research Methodology
Pre-project, Feasibility and Foundation : Select Methodology
Pre-project, Feasibility and Foundation : Project Gantt Chart
Pre-project, Feasibility and Foundation : Meet Project Advisor
Pre-project, Feasibility and Foundation : Meet Co-ordinator
Pre-project, Feasibility and Foundation : Co-ordinator Approval
Pre-project, Feasibility and Foundation : Complete Project Proposal
Pre-project, Feasibility and Foundation : Complete Gantt Chart
Analysis and Design Documents : Website Analysis and Design Document
Analysis and Design Documents : Client Application Analysis and Design Document
Analysis and Design Documents : Database Evaluator Analysis and Design Document
Exploration Phase : Iteration One : Website : Plan Website and Choose Wordpress Template
Exploration Phase : Iteration One : Submit Test Report Iteration One (Website)
Exploration Phase : Iteration One : exe App: Client Application Design
Exploration Phase : Iteration One : Submit Test Report Iteration One (.exe App)
Exploration Phase : Iteration Two : Website : Program the Register Form
Exploration Phase : Iteration Two : Website : Program the Login Form
Exploration Phase : Iteration Two : Website : Verification of the Customer Email Address
Exploration Phase : Iteration Two : Website : Basic Account User Page
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (Website)
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic GUI Design Unit and Test
Exploration Phase : Iteration Two : exe App : Create Virtual SQL Server Test
Exploration Phase : Iteration Two : exe App : Basic Saving of Dump file with Test
Exploration Phase : Iteration Two : Submit Test Report Iteration Two (.exe App)
Exploration Phase : Iteration Three : Website : Download of the .exe App from the Website
Exploration Phase : Iteration Three :Create Basic Contact Us Page with Forms
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (Website)
Exploration Phase : Iteration Three : exe App : Install Different version of SQL Server
Exploration Phase : Iteration Three : exe App : Completely Working GUI
Exploration Phase : Iteration Three : exe App : Dump file Saving with Testing
Exploration Phase : Iteration Three : exe App : Encrypted Dumpfile with Testing
Exploration Phase : Iteration Three : Submit Test Report Iteration Three (exe. App)
Engineering : Iteration One : Website: Upload of Customer Parameters or PDF to Website
Engineering : Iteration One : Website: Forgot Password Function Page
Engineering : Iteration One : Submit Test Report Iteration One (Website)
Engineering : Iteration One : exe App : Database Evaluator Basic GUI Design with Unit Testing
Engineering : Iteration One : Submit Test Report Iteration One (.exe App)
Engineering : Iteration Two : Website: Create Documentation Page
Engineering : Iteration Two : Website: Design All the Pages of the Website and Create all the Images needed
Engineering : Iteration Two : Website: Add Plugins and Review all links
Engineering : Iteration Two : Submit Test Report Iteration Two (Website)
Engineering : Iteration Two : exe App: Database Evaluator Basic Generator of PDF Report with Unit Testing
Engineering : Iteration Two : Submit Test Report Iteration Two (.exe App)
Engineering : Iteration Three : Website : Notification Email for Customer and Developer
Engineering : Iteration Three : Website : Upload the Website Online and Test all function if working
Engineering : Iteration Three : Submit Test Report Iteration Three (Website)
Engineering : Iteration Three : exe App : Database Evaluator + Client Application Working Properly
Engineering : Iteration Three : Submit Test Report Iteration Three (.exe App)
Deployment : Combine Website, Client Application and Database Evaluator
System Test : Test Plan for System Test
System Test : Test Case for System Test
System Test : Test Results for System Test
System Test : Check all the Phases If all Requirements were Delivered
Post Project : Review Project
Post Project : Collating Documents
Project Admin : Project Diary
Project Admin : Personal Logs
Project Admin : Timesheet
Project Admin : Create Supporting Documents
Meeting : Frequent Face-to-Face Meeting with Team Members
Meeting : Weekly Meeting with Project Advisor
Meeting : Consulting Robert For Documents Review
Project Audit : Project Audit 1
Project Audit : Project Audit 2
Presentation Preparation : Project Presentation
C# R&D
SQL Server R&D | Building SQL Server Scripts and Test
WordPress R&D
Absent : Sick Leave